## Boss issues
S.No | Category | Issue Description | Steps to Reproduce | Dev Status | QA Status | Proof
1 | UI | 1.Groups page - When click on the group in breadcrumb. The breadcrumb is hidden 2.Select checkbox and Click on delete button does not show any confirm message. 3.Action - Edit - After editing one time. The edit icon is not shown for second time fo edit 4.Select users page - Alignment issue and access rights not showing properly | 1.Go to Boss and open setup menu 2.Select groups.Select the checkbox and click delete |  |  | issue1
2 | UI | 1.Business rules Page - UI not changed properly 2.Check boxes and actions icon are present for the default values 3.Edit - Popup displaying not correct. 4.Delete activities - Using check box and delete. It doesnot throw an confirm message. 5. If we add and delete the activities and create the same activity which is deleted and saved. It is not added. 6.Levels cannot be set for activities. After setting level and save. It does not shown. 7.Clicking on reset level icon showing the level reset successfully. But there is no level selected. Alert message showing wrongly. |  |  |  | issue1
3 | UI | 1.Other interested party - Breadcrumb showing wrongly 2.Adding other interested party page - Add address - Defaultly showing the state and city without choosing country. And after save it is not saved and records is not displayed. 3.The records not able to delete. But shows the alert message "deleted successfully" |  |  |  | issue1
4 | UI | 1.Customize email messages - Breadcrumb is not present 2.Click on save button does not throw an alert
5 | UI | 1.Supplier - breadcrumb UI not correct 2.Supplier creation page - Breadcrumb UI not correct, Multi language not handled showing as THL. And for supplier name and supplier code text filed showing as alert with 'THL'(refer image- 5.2). Scroll down is present. Page is not proper. 3.SQI Engineer and manager select users page having + icon for done button and having 2 scrolldowns 4.search - Registration status - Not having dropdown |  |  |  | issue2
6 | UI | Schedule update for reports page - showing server error
7 | UI | 1.Customer - Cannot able to delete customer 2.Cannot able to enter (add) customer priority, industry, business unit 3.Also added customer address and customer part number details are not getting saved |  |  |  | issue2
8 | UI | 1.Keyprocess - while selecting global process owner the pagination hidden and not shown 2.When delete the key process, the Confirm message having UI issue. 3.When delete the key process shows the above alert(with global process owner and without it)(refer images).Not able to delete. 4.Pagination is not showing correctly and Ui issue in it. Also site selection is there but in previous UI not there. 5.Edit process information button is not working.Does not show anything 6.While without selecting any row, click on the copy to other process scope shows the above alert.(image-8.6) 7.copy to other process scope page - UI not proper, Pagination is not placed properly |  |  |  | issue2
9 | UI | 1.Competitor page - If we check in all the checkboxes and leave one from it and delete it. The records which is unchecked gets deleted and which checked not gets deleted.
10 | UI | 1.Teams - select entity page - done button Ui change 2.Teams - Select users page - not proper in alignment and done button having + icon 3.Add members - while delete shows the above alert after confirm message. Can't able to delete 4.External members - add button not work in the teams page |  |  |  | issue3
11 | UI | 1.Template - Added one cannot be deleted using actions menu. If we delete through checkbox it reload the page and not deleted. 2.While adding the forms and without enter the data click save. It doesnot show an alert and it closes the popup without alert message. 3.Saved and updated messages are shown in orange color |  |  |  | issue3
12 | UI | 1.Template properties - Click and open the menu shows the above alert(image)

## issue1
1.4 |  | 2.1 | 2.2
| 2.3 | 2.7
3.1 |  | 3.2

## issue2
| 5.1 |  | 5.2
5.3
7.2
8.1
8.2
8.3
8.6
8.4
8.7

## issue3
10.2 | 10.3
12.1