## Sheet1
S.NO | PAGE | ISSUES | PRIORITY | REPORTED BY | DEV STATUS | QA STATUS | COMMENTS
1 | Report Date | Include all dates in the reports as per user preference | suggestions
2 | Action Item Status dropdown -ECR Form | Is it possible to indicate the status of actions as a dropdown insite the form | suggestions
3 | Change Checklist | 1.Need to corret spelling in the search and field name- Space and Caps L not needed (Checklist) | medium
2.Checklist search is not woring under assign checklist
3. Scroll bar is not showing for assign checklist
4. Department need to be site specific(Assign checklist)
5. Department which is not assigned to any site also listed under assign checklist deprtment dropdown.
6. Checklist created in the setup need to be site specific
4 | non mandatory approver | 1.for nonmandatory approver workflow, form not closed after approvers approval , its in implemened status | medium
2.in view log, showing all the approvers ( not approved approver also showing with dates in view log)
3.for under view status ,approver not listing in approver section ( while opening from status page)
4.for 2 mandatory & 2 non mandatory approver --after CR approved,while opening CN from status page CR approver section showing 2 approved approver & CN approver section showing 4 approver
5 | project - by using assign approver | once project created with assign approver user, while publishing plan for APQP project,approval goes for category (old approver) only | medium
6 |  | 1.click on change category ,select position base routing | medium
2.initiate change request
3.then remove position base route & set default route as auto approval
4.again initiate change request
5.observe approver section
6.then publish the form and observe the changes(its showing position based routing popup)
7 | Documents to change - subforms | once external document added , not able to edit it on second time | medium
8 | CM Actions | Whether this menu is needed for a user who is not having CM group rights? | Suggestions
9 | Widget | CM Widget is showign all initiated CRs for a user without module rights | low
10 |  | Need to Remove publish from right click | Suggestions
11 | Multiple document selection need to be restricted in Documents subform | Multiple document selection need to be restricted in Documents subform | low
12 | Husco- | Approver is not showing in the form based on doc control group selection but the action item is sending to that user | low
13 | MG- PCR | Selected date is greater than the current date is getting for predicted date of deilvery(need future date) | low
14 | PCR-add document - link | in add document section ,after form get closed link is not opening(i.e: revision number & | Medium
attached document link)
15 | wavier & gabriel -change request status page | while giving special character in form, not able to open form from status page | Medium
16 | business rule | Evidence Document mandatory uncheck is not validating any of the pending actions from CN | low
1. Risk actions
2. Document Revision by Resp person
3. Project Completion
17 | wavier | while comments not given by approver ,its shows empty in form & for auto approval also comments showing empty in form | Medium
18 | Multi site-Brakepoint | CR Number editable in Brakepoint form | medium
19 | Multi site | Action item not showing for resp person- Blockage(corp user is given for action) Applicable for all forms | medium
Waiver approval Action, Team sign off also not showing
20 | PCR- cft sign off section | while we select cft members in setup for PCR but it follows the sub form cft sign off members,when sub forms submit & submit to team buttons clicked(NOTE: after refresh its shows correct) | low
21 | Overall sub form | Delay in saving data, especially in finance form | suggestions
22 | PCN Form Suggestion | Allowing to switch to Aqua yes no at a time after entering data - suggestign to give an alert or clear data on switching between checkbox | suggestions
23 | ECN | part name section need to lock (when part name is already selected in CR, we can able to change in CN also) | suggestions
24 | efectiveness tracker (multi site) | effectiveness tracker , not given as site specific | medium
| horizontal deployment (multi site) | horizontal deployment , not given as site specific | medium
25 | Usability- Part tree search | Part tree search is showing partially when clicked from left corner | Suggestions
26 | Horizontal deployment -Form | 1. PI selection popup in applicable product name should close automatically on clicking done. | Suggestions
2. Pi search is not working
3. Delete row option is needed for Blank Horizontal deployment form during initiation time itself
27 | doc pro | published risk form in doc pro , not showing full view | medium
|  | Disable cehckbox and text fields in feasibility form if there is no considerations added | Suggestions
28 | ECR & waiver - cn rejection | 1.cn rejected by approver | medium
2.open rejected cn from status page
3.click on revise document button
4.observe cn approver section(cn approver section shows empty but when click on publish , actions goes for particular approver)
29 | effectiveness tracker & horizontal deployment | not showing the CR full list based on closed status (NOTE : not replicating in 54 site) | low
30 | Manufacturign Feasibility Report | Need to lock Supplier code and name, allow to select ppap initiated date as past/current date | suggestions
31 | Copy Form | Target date for the CR form is not gettign saved | low
| copied risk form | action item not goes for responsible person | medium
32 | Sugesstion- Close CR | Suggesting for a confirmation message while closing CN using CLose button | suggestions
33 | cft rejection | when cft member reject the form without comments , in view log its shows waiting for signoff | medium
34 | CR rejection | 1.initiate change request | medium
2.publish CR form & reject
3.open rejected form from status page
4.click assign approver button
5.select approver as initiator & then publish
6.open CN from status page
7.observe cr & cn approver section (in cn section showing old approver name instead of newly selected approver name , but when click on publish action items goes for newly selected approver only)
8.& while opening closed PCN from doc pro ,CN approver section shows empty
35 | Design changes | all CM forms label and design changes | suggestions