## Sheet1
S.No | Page Name | Issues | Priority | Dev Status | QA status | Comments
1 | search | search option not working | medium | Completed in site | fixed in cloud | for inactive status its shows counting wrong
2 | CR form setup - sub form template mappping | need to restrict other forms listing in finance & breakpoint template mapping section | suggestion | Not Required |  | Not Required
3 | PCR form | pcr number section editable , need to give alert | suggestion | Completed | fixed in cloud
4 | business rule | on default (enable adhoc route,team submission,copy option,automatic close request - business rule only need to show as enable , remaining all business rule need to show as disable) | suggestion | fixed | fixed in cloud | 1.duplicate change request title need to disable 2.automatic close change request need to enable
5 | numbering format | delete option not working in edit numbering format section | high | fixed | fixed in cloud
6 | cft setup | not able to select responsible person | high | fixed | fixed in cloud
7 | consideration & risk setup & documents to change | once same data entered for 2 change category and editing data in 1 change category, data in another change category also changed | medium | fixed | fixed | for documents to change not fixed
8 | consideration | on default data's not showing, after we change the category only data's showing | low | fixed | fixed in cloud
9 | attachment - link | while opening attachment link ,its says please contact administrator or technical support | medium
10 |  | after entering change title, when we try to close/cancel the change request ,its shows popup do u want to continue,in that popup yes button not working | high | fixed | fixed in cloud
11 | business rule- duplicate change request | need to interchange the work flow ( enable work flow need to give as in disable flow & disable work flow need to give as in enable flow) | suggestion | fixed | fixed in cloud
12 | attachment - link | while attaching attachment , at the time not able to change or delete that attachment, its shows please contact administrator or technical support | medium | HOLD | HOLD | on second time deleting,its not fixed
13 |  | Based on a business rule, Change Title will be allowed to duplicate once the existing CR with same name gets closed and CR title will be prefixed with CR number for Project name | high | Fixed - reverify |  | not able to publish project plan( Need to restrict Sending /*¦\ symbols for APQP projects)
ISSUES:
|  | 1. without closing existing CR we can able to generate new request with duplicate title |  |  | 1.fixed in cloud
|  | 2. CR title will be prefixed with CR number for Project name--- not listing in APQP project page |  |  | 2.fixed in cloud
|  | 3.duplicate change title project , not able to publish plan in APQP |  |  | 3.fixed in cloud
14 |  | Not to list CR with no name, CR Number - generate after CR title | high | Fixed - reverify
ISSUES:
|  | 1.without change title when, we try to close/cancel change request , its want to show popup do u want to continue but now with change title that popup showing |  |  | 1.fixed in cloud
|  | 2. do u want to continue popup-- yes button not working |  |  | 2.fixed in cloud
|  | 3.while closing/cancel the change request ,its redirects to initiate change request page |  |  | 3.fixed in cloud
|  | 4.on second time cancel/close change request, do u want to continue popup not showing |  |  | 4.fixed in cloud
|  | 5.on second time clicking cancel/close change request,its redirects to initiate change request page |  |  | 5.fixed in cloud
15 | customer waiver approval section | while clicking submit waiver check box,its shows system.net web exception | high | Fixed | fixed in cloud | Verify in Cloud
16 | business rule-automatic close change request disable | CN will be allowed to publish even if the project is not completed. | high | fixed
Once after CN approval, CR remains in implemented status.
Only after project completion, User will be allowed to close the change request.
ISSUES :
|  | 1.not able to publish cn without project completion, its shows project is not completed |  |  | 1. fixed in cloud
|  | 2.without project completion when try to click close change request button , need to show alert |  |  | 2. fixed in cloud
|  | 3.close change request button not working |  |  | 3. fixed in cloud
17 | business rule-automatic close change request enable | 1.after cn approval , change request not get closed,its in implemented status only | high | fixed | 1.fixed in cloud
|  | 2.close change request button not working |  |  | 2.fixed in cloud
|  | 3.without project completion ,when we try to click close change request button , (that project not completed alert disappears quickly and showing pending action popup) |  |  | 3.fixed in cloud
18 | detailed risk form setup | route tab showing all modules routes | low | Not an issue | Not an issue
19 |  | inside the form department section showing department on default without mapping any department for that user | high | fixed | fixed in cloud
20 |  | auto module approval route not listing in route selection | medium | fixed | fixed in cloud
21 |  | pending action popup , save/done button need to be unique | low | fixed | fixed in cloud
22 |  | To add users from different sites in the CM module.- CFT Section and Customer Waiver Setup, Sub form Reviewers | high | Verify in Cloud |  | Verify in Cloud
ISSUE :
|  | 1.customer waiver approval setup not listing other site users |  |  | 1.fixed in cloud
|  | 2.action item not goes for other site users |  |  | 2.fixed in cloud
23 | basic risk form setup | basic risk form setup, not showing in full view |  | fixed | fixed in cloud
24 | Sections editable in PCR form | 1. Plant Name | low | Completed | 1.fixed in cloud
|  | 2. Purpose |  |  | 2.fixed in cloud
|  | 3. trigger for change |  |  | 3.fixed in cloud
|  | 4. Types of proposal |  |  | 4.fixed in cloud
|  | 5.Risk Analysis form (High risk,medium, low) |  |  | 5.fixed in cloud
25 |  | Multiselect delete option | medium | fixed
ISSUE:
|  | 1.while deleting multiple change request , only one change request is get deleted |  |  | 1.fixed in cloud
|  | 2.alert - delete sucessfully alert not showing content |  |  | 2.fixed in cloud
26 | Numberign format issues | 1. Allowign to delete existing numbering format | high | fixed | 1.fixed in cloud
|  | 2. Allowing to edit format already mapped with category |  |  | 2.fixed in cloud
|  | 3. Edit numbering format need to show the new numbering popup for set up |  |  | 3.fixed in cloud
27 | Change Request alert w/o title | Please enter the Change Title to save this request.Do you want to continue? suggesting to change this alert as the user is not aware that on clicking no the CR will get deleted on clicking no, | suggestion | fixed | fixed in cloud
28 | cr form setup | new/edit template mapping section, active and inactive status counting list showing wrong | low | Fixed | fixed in cloud
29 | numbering format | numbering format page listing showing wrong | low | Fixed | fixed in cloud
30 | set default numbering format | deleted numbering format also listing in set default numbering format section | medium | fixed | fixed in cloud
31 | numbering format | 1.once numbering format is deleted ,again with same numbering format not allowing to add | high | Fixed - reverify | 1.fixed in cloud
|  | 2.edit button not working on single click |  |  | 2.fixed in cloud
|  | 3.once numbering format get edited, it will save as new one ,not get edited on same format |  |  | 3.fixed in cloud
32 | widgets- change request actions | if we assign cft members &reviewers from multi site, action items not shows in change request actions widget for that assigned site | medium | fixed | fixed in cloud
33 | finance form-cost owned tooling section | tooling and equip error proffing section-on first time clicking check box enabled in cost owned tooling section and on second time clicking only able to enter data in tooling section( suggestion :on first time clicking need to enter data and as well as check box also need to enable) | suggestions | Not an issue | Not an issue
34 | department | when we inactive user assigned department in cross functional team setup, if we mapped that same user for subforms there also department not shows | medium | fixed | fixed in cloud
35 | business rule-enable duplicate change request title | once we give same Title for 2 or more change request,while clicking publish ,its says change request is in open status ( note: both the request is in open status) | suggestions | fixed | fixed in cloud
36 | numbering format | numbering format listing in pcr form,shows wrong count | medium | fixed | fixed in cloud
37 | numbering format | while clicking numbering format button , its take time to load & while clicking edit button in edit numbering format section also taking time to load | suggestions | Fixed
38 | assign department | 1.if we map user for multiple department, on default which department need to show..? | suggestions | Fixed | 2.fixed in cloud
2.initiated department from form ,showing all departments in the dropdown
39 | numbering format | new/edit numbering format popup view need to give as collapse view, like change checklist setup | suggestions | Fixed | fixed in cloud
40 | esclation & reminder | 1.customized mail messages - newly added mail not showing content | high | fixed | 1.fixed in cloud
|  | 2.mails got interputted in BM |  |  | 2.fixed in cloud
41 | numbering format | if numbering format is not mapped and user try to initiate change request , its shows please enter numbering format alert but we cannot able to close that change request popup directly | medium | Fixed | fixed in cloud
42 | new/edit template mapping section | if we select all form status as inactive , then in search section try to search active status its shows inactive status only( note: but actually it want to show no record found) | low | Fixed | fixed in cloud
43 | new/edit template mapping section | 1.if we delete particular form from new/edit template mapping section, its shows blank alert | medium | Fixed | fixed in cloud | Delete option will be removed
2..if we delete particular form from new/edit template mapping section, form not get deleted
44 | sign off section - ECR & waiver form | while we add cft member from form itself by using right click add option, department not listing for that user | medium | Fixed | fixed in cloud
45 | sign off section - ECR & waiver form | while we add cft member from form itself by using right click add option, multi site users not showing | medium
46 | Label Issue | THL- showing in business Rule | low | Fixed | Fixed in cloud
47 | Route | Escalation Route not saving in suite | medium | Fixed | fixed in cloud
48 | Change Chekcklist | Error page showing | high | Fixed | Fixed in cloud
49 | Business Rule | Is mandatory Change title need space & space needed for above and this section | medium | Fixed | fixed in cloud
50 | is mandatory business rule- disable | if we initiate change request with diisable work flow, we can able to initiate change request but that initiated change request not shows in status page | high | Fixed | fixed in cloud
51 | Business Rule | business rule need to give as site specific | suggestions | Not Required
52 | Business Rule | Suggesting text change for Copy form like Copy change request) | suggestions | Inprogress
53 | customer waiver approval-action page | action created date for customer waiver approval already removed but its showing now as 1900 | low | Inprogress |  | Action date to be included .. But not for Android release but bfr 11.2.0.2 sign off - remove 1900
54 | Business Rule | on second time enable , disable work flow in business rule ,its not shows saved successfully alert | suggestions | Not an issue
55 | route listing page | on default its showing all modules route, after refresh only its shows CM route | low | Inprogress
56 | suite - assign department | once user mapped in particular department, after we not able to uncheck that check box , its shows dependency exit data but even if we not created any request | low
57 | suite - assign department | once checkbox checked in assign department section( yellow clour), that department will show in cft setup but after uncheck that checkbox in department section also that department listing in cft setup page | medium
58 | cft setup | if same department mapped for different sites ,in cft setup responsible person selection popup showing all sites user mapped for that same department. is that correct work flow....? |  | Not an Issue
59 | cft setup | in cft setup page if we set active status for 2 dept with same user and select that user as one of the reviewers for subforms , while initiating change request , cft sign off section for that mapped user subform showing duplicate user name | high | Inprogress
60 | consideration & risk & documents to change setup | once same data entered for different category , that particular data related all details automatically generated in newly created one | low
61 | Target Date | Suggesting to show escalation reminder mails date based on CFT target date | suggestions | TBD
62 | inbox mail - notification of action item | notification of action item mail subject changed as change request actions, subject need to shows as notification for action item | low
63 | pending action popup | pending actions are not listing in pending action popup | medium
64 | remainder & esclation | 1. remainder mail not generated for task owner | medium | fixed | fixed in cloud
2. change request actions remainder mail- not generated in batch manager
3. change request actions - remainder mail only generated for task owner( Note: 2nd ,3rd round mail also generating to task owner only not for round approvers)
4.reminder mail is not getting removed after submission by team
5.customer waiver approval - change request actions mail interputted
6.customer waiver approval - change request actions mail not getting in inbox
7. customer waiver approval - completion mail not generated in batch manager