## Sheet1
S.No | Page Name | Issues | Priority | Dev Status | QA status | COMMENTS
1 | MG Form | Need to lock fields inSub supplier form for part number category all are editable now | low | Fixed | Fixed in cloud
2 |  | SQE with Group rights- After giving group rights and opening from SM portal getting an alert popup and CR also showing wrong | medium | Fixed | Fixed in cloud
3 | automatic close change request business rule enable | in implemented status when we try to close change request by using close change request button, it shows alert "CR cannot be closed as CN is waiting for approval", that alert colour need to change as orange | suggestions | Fixed | Fixed in cloud
4 |  | please map numbering format of subforms alert , need to rename as " please map numbering format for subforms" | suggestions | Fixed | Fixed in cloud
5 | automatic close change request business rule enable & disable | in implemented status when we try to close change request by using close change request button, it shows alert, that alert should be unique for both enable & disable workflows. | suggestions | Fixed | Fixed in cloud
1.for enable work flow --it shows alert "CR cannot be closed as CN is waiting for approval".
2.for disable work flow ----it shows alert "change notification form is waiting for approval".
6 | PTDB form | 1.is publish button needed for PTDB form ..? | medium | Fixed | 1.Fixed in cloud
|  | 2.auto populated fields like plant, customer , product name,LHRH,customer plant, reported date,cause sections are editable -- need to lock this fields |  |  | 2.Fixed in cloud
|  | 3.applicablity check box not able to check |  |  | 3.Fixed in cloud
|  | 4.concern closure date,implementation date and target date not able to select ,its shows alert |  |  | 4.Fixed in cloud
|  | 5.concern description section is text entry field or auto populated field..? |  |  | 5.Fixed in cloud
|  | 6.occurance action,justification, action plan,detection action,lesson learnt section -- not able to enter data |  |  | 6.Fixed in cloud
|  | 7.responsible person shows number format and data not get saved |  |  | 7.Fixed in cloud
|  | 8.horizontal scroll bar not user friendly |  |  | 8.Fixed in cloud
|  | 9.PTDB form not based on change request specific( if we edit PTDB form data 's in one change request it will replicate in another chane request also) |  |  | 9.Fixed in cloud
7 | ECR Form | need to lock fields in ECR form ,(Reason for change, Benefits of change,Dimensions,Documents to change) | medium | Fixed | Fixed in cloud
8 | decision on stock | if we change cft user in multidisciplinary section,that changed user in decision on stock section get duplicated | medium | Fixed | not fixed | Moved to next release ,so closing from this sheet
9 | change management setup -- search dropdown | 1.cross functional team setup -- need to remove site in search drop down | medium | Fixed | 1.Fixed in cloud
|  | 2.documents to change setup--- Department search not working |  |  | 2.Fxed in cloud
|  | 3.change category-- status search not working |  |  | 3.Fixed in cloud
10 | all forms - dropdown selection | 1. on multiple times selecting data's in drop down , its shows alert | high | Pending | not fixed
|  | 2. Not allowing to select “select” option from dropdown once a value is selected applicable for all forms |  |  |  | Moved to next release ,so closing from this sheet
11 | auto approval - subforms | if we set auto approval for subforms , and publish the forms , approver section get blank and published form in doc pro shows check box unchecked | high | not replicated in 46 | not fixed | Moved to next release ,so closing from this sheet
12 | sub forms cft sign off | if we set same user for subforms cft sign off and main form cft sign off, when we change that user in multidisciplinary section, subforms cft user also getting changed | high | Fixed | Fixed in cloud
13 | Process change form | Request sent on date is allowing future date only | low | Fixed | Fixed in cloud
14 |  | Sub form Department( If not dept mapped)-text box is editable and showing error | medium | Fixed | Fixed in cloud
15 | Risk Feasibility | Responsible person can edit target date in feasibility/Risk form | low | Fixed | Fixed in cloud
16 |  | PCN- Internal ppap date ia allowing to select old date, and on selecting future date it is showing alert as “ selected date is less than current date” | low | Fixed | Fixed in cloud
17 |  | After Refreshing PCN- Not able to edit/delete attached document for ppap attachment section | medium | Pending |  | Moved to next release ,so closing from this sheet
18 |  | User without mod rights is able to view all request in listing, Correct view is available in status count section. | medium | Fixed | Fixed in cloud
19 | PCN Form - implemented status | need to lock fields in PCN form ,after CN approved by approver (stock or WIP quantity section,expected implemented date section,change validation responsible person section,input for validation- text entry field& attachments section,internal PPAP section,PPAP approval section,notification section, evidence section,change implementation-date ,shift, invoice number,attachments section) | low | Fixed | Fixed in cloud
20 | alert | 1.initiate Change request | medium | Fixed in 46 | Fixed in cloud
2.navigate to subform and publish it
3.then navigate to main form and publish it
NOTE: in this scenario after refresh only publish button not showing in main form but without refresh when we publish the form ,it will get published ,need to give alert for that like team sign off
21 | documents to change | 1.on default data's not showing for the 1 st category | low | Fixed | 1.Fixed in cloud
|  | 2.if we delete data's in particular category , dependency data's also getting deleted |  |  | 2.Fixed in cloud
22 | Issue #2- Related issue | Created multiple CR's and for SQE login count mismatch happened, Status shows 3 count and listing showing 2 only | medium | Fixed | Fixed in cloud
23 |  | set multiple approver in change category setup( like user1,user2,user3,user4) | medium | fixed | Fixed in cloud
1.initiate Change request by user1
2.then login with user2 and publish the form
3.action item goes for user1 but check box is disabled
24 |  | Deleted Succcessfully alert should be in Red color as per UI | low | Need clarity
25 | FOrm design | Risk Assessment form is showing PH and COO in the Sign off section in the design | medium | Fixed | Fixed in cloud
26 | Business Rule | Change the Enable adhoc route text as Modify Approvers | medium | Fixed | Fixed in cloud
27 | TDR From Docpro | Not able to initiate new request and View log , OPen CR from Docpro menus*Rejected,ongoung TDR option* | medium | Fixed | Fixed in cloud
28 | Multi Disciplinary approach | 1. When a team member is replaced then the department also need to be changed based on the user selection | low | Fixed | 1.Fixed in cloud
|  | 2. When One user is selected dont allow to select the same user in the next row |  |  | 2.not fixed | Moved to next release ,so closing from this sheet
29 |  | Source Ref # is not autopopulated once initiated from APQP | low | Pending
30 |  | Suggesting to change the alert as "Please map feasibility form in the setup " if subforms are not mapped | medium | Fixed | Fixed in cloud
31 | feasibility report subforms - design (106 series) | feasibility report subform , sign off section date field border line missing | low | HOLD |  | Moved to next release ,so closing from this sheet
32 | risk setup | sorting not working for parameter | low | Fixed | fixed in cloud
33 | cft user in subforms | when we add cft user from form itself by using right click add , that added cft user not listing in subforms , when there is no reviewers set in the setup for subforms | low | Fixed | Fixed in cloud
34 | copied form- pcr | 1.for sub forms -already mapped responsible person not able to change and need to remove completion date | high | Fixed | Fixed in cloud
35 | sub form - risk | not able to select target date in risk sub forms | medium | Fixed | Fixed in cloud
36 | sub forms | if subform get refreshed , not able to select responsible person & once any data entered into subforms that time not able to select responsible person ( 46 site) | medium | Not an issue
37 | Multi line Change title | The CR initiated with multi line change title , After publish The CR and Cn is not openign from status |  | Fixed | Fixed in cloud
38 | remainder & escalation mail | 1.need to remove dear all in remainder and escalation mail | medium | Fixed | 1.Fixed in cloud
|  | 2.content need to change like - "this is remainder mail to notify","this is escalation mail to notify" |  |  | 2.Fixed in cloud
|  | 3.escalation mail also having same content as remainder mail - for the top heading |  |  | 3.Fixed in cloud
|  | 4.dept review mail- need to remove time |  |  | 4.Fixed in cloud
|  | 5.dept review escalation mail- date not generating |  |  | 5.Fixed in cloud
|  | 6.team sign off mail link is not visible |  |  | 6.Fixed in cloud
|  | 7.team sign off target date spelling need to correct |  |  | 7.Fixed in cloud
|  | 8.team sign off escalation mail not showing tabular column |  |  | 8.Fixed in cloud
|  | 9.team sign off mail- while we add target date , tabular column get duplicated |  |  | 9.Fixed in cloud
39 | multi disciplinary section | in multi disciplinary section, not able to select multi site user | medium | Fixed | Fixed in cloud
40 | PTDB FOrm | Data entered for the closed concern is not showing in PTDB form(closure date, concern desc, Occurence ) | high | Fixed | Fixed in cloud
41 | numbering format alert | if numbering format not mapped in setup,and try to initiate change request , its shows alert " please map feasibility form template in the setup" ( that alert content need to change as " please map numbering format for subforms" ) | medium | Fixed | Fixed in cloud
42 | view log | view log - sign off section not getting loading ( note :for CR form its opened , CN only not get loading) | high | Fixed | Fixed in cloud
43 | view log | view log - team sign off & dept review section not getting loading , when subforms are send for team sign off & dept review | high | Fixed | Fixed in cloud
44 | SUBFORM VIEW IN CN- | For the subforms which is not published from CR It is allowing to do functionalities like publish, review... from CN . Is this workflow ok? |  | not an issue
45 | mail -cft | 1.mail interput in batch manager | medium | Fixed | 1.Fixed in cloud
|  | 2.based on the target date , frequency set for the before mail is not getting in BM |  |  | 2.Fixed in cloud
46 | multi disciplinary section | not able to change user in multi disciplinary section,while selecting user its shows number format &"system data sql exception" alert ( note : for one particular user only) | medium | Fixed | Fixed in cloud
47 | cft - rejection | 1.with comments when user try to check rejected check box ,that time also ( please fill comments popup box showing), need to remove popup box | medium | Fixed | Fixed in cloud
|  | 2.without comments when user try to check rejected check box, it shows (please fill comments popup box) but clicking ok button in that popup , rejected check box get automatically checked |  | Fixed | Fixed in cloud
48 | risk analysis - sub form | design - implementation rating section outline design missing | low | Fixed | Fixed in cloud
49 | process change progress tracker | 1.plan & actual section - whether date need to show (or) count need to show ? |  | Fixed | Fixed in cloud
|  | 2.approval from CQA ,customer approval - data populated from which section? |  | Fixed | Fixed in cloud
|  | 3.need to give status filter also in report |  | Fixed | Fixed in cloud
|  | 4.whether all status record need to show in report (or) only need to show closed status record |  | Fixed | Fixed in cloud
|  | 5.reports date not showning as user preferences date |  | Fixed | Fixed in cloud
|  | 6.change validation section, plan date not showing |  | Fixed | Fixed in cloud
|  | 7.output document updation section , actual count not showing |  | Fixed | Fixed in cloud
|  | 8.change validation section- plan & actual section showing date , need to show count value |  | Fixed | Fixed in cloud
50 | mail -cft | 1.reminder mail - link not shows like hyper link | medium | Fixed | Fixed in cloud
|  | 2.in batch manager for all the 3 mail ( reminder, escalation, pending )- showing content heading as remainder , need to change the content for pending, escalation. |  | Fixed | Fixed in cloud
|  | 3.pending action mail not generated in batch manager & inbox -- ( note: instead of pending action mail , now showing reminder mail only) |  | Fixed | Fixed in cloud
|  | 4.reminder : pending task mail - hyper link not showing |  | Fixed | Fixed in cloud
|  | 5.reminder : pending task mail - date format need to change as 21/feb/2023 |  | Fixed | Fixed in cloud
|  | 6. team sign off, dept review, responsible person mail- for all the mail date format need to change as 21/feb/2023. |  | Fixed | Fixed in cloud
|  | 7.for dept review escalation mail- showing reviewers & regards as tabular column |  | Fixed | Fixed in cloud
51 | PTDB FOrm | 1.PTDB planned & implemented actions count not showing in PCN form and pending action popup | medium | Fixed | Fixed in cloud
|  | 2.occuerence spelling mistake ,need to change spelling as occurrence |  | Fixed | Fixed in cloud
|  | 3.for responsible person - target date , responsible person section editable need to lock |  | Fixed | Fixed in cloud
52 | Action Termination and replacing user actions to another user | 1. not able to terminate subforms | medium | Fixed | Fixed in cloud
|  | 2. ( both main & subforms) terminate action not working for dept review , on clicking no response |  | Fixed | Fixed in cloud
|  | 3.when we change subform reviewer from view log , that changed reviewers will reflect in main form reviewers section ( note: after refresh it shows correct) |  | Fixed | Fixed in cloud
|  | 4.not able to send dept review for second time , when we change user in viewlog for second time ( note: applicable for both termination and modify approvers) |  | Fixed | Fixed in cloud
|  | 5.CR cft user not able to modify -Data not found |  | Fixed | Fixed in cloud
|  | 6.modify approver icon not showing for CN dept review -- is it ok ? |  | Fixed | Fixed in cloud
|  | 7.when we click cancel or close popup icon in the user confirmation popup --after that try to seect users by using modify approvers icon,that selected user not getting saved & user alert confirmation popup not shows for second time selection |  | Fixed | Fixed in cloud
|  | 8.if initiator and cft user is same for subforms , for that user when we click terminate icon on viewlog , form not get auto refreshed |  | Fixed | Fixed in cloud
|  | 9.if initiator and cft user is same ,when we terminate initiator user in viewlog , after the form get loaded check box are enabled , need to lock that checkbox |  | Fixed | Fixed in cloud
53 | initiate change request page | while initiating change request ,its shows server error for some change category ( waiver, machinery, ecn impl,document, etcc..) | high | Fixed | Fixed in cloud
54 | subforms - department | for subforms - department not showing in subforms ( note: for this issue fix already given) | medium | Fixed | Fixed in cloud
55 | process change progress tracker - report | 1.applicable machine & applicable line showing same data in reports | medium | Fixed | Fixed in cloud
56 | HUSCO | Husco Items in the pending list to be fixed | high
|  | 1. Approver is not showing in the form based on doc control group selection but the action item is sending to that user |  | Fixed | Fixed in cloud
|  | 2.While we initiate change request from APQP with approver , that approver not listing in CR approver section |  | Fixed | Fixed in cloud
|  | 5.Custom workflow- When modifed approver in the form then it should show both doc control approver+adhoc in the form. Now it is showingonly after publish |  | Fixed | Fixed in cloud
57 | report - process change progress tracker | 1.applicable product name showing number , instead of name | medium | Fixed | Fixed in cloud
|  | 4.approval from CQA - received date is showing as initiated date,instead of maura owner approved date |  | Fixed | Fixed in cloud
|  | 5.effectiveness tracker we have multiple section data's , then in reports which section data need to show in start date /month section ? |  | Fixed | Fixed in cloud
58 | horizontal deployment & effectiveness tracker | machine name not populated in , horizontal deployment & effectiveness tracker | low | Fixed | Fixed in cloud
59 | action management -action created date | action created date for PTDB form shows diff date | low | Fixed | Fixed in cloud
60 | auto approval | for auto approval , CN form approver listing wrong user but when we click publish button form get auto approved and approval status for CN not shows in viewlog | high | Fixed | Fixed in cloud
61 |  | Sign off --- action termination & modify approver
|  | 1.team sign off terminate -- when we click terminate icon ,its shows confirmation popup , in that confirmation popup when we click ok button ,its shows alert action is successfully terminated ( need to remove confirmation popup when we click ok button & action is successfully terminated alert need to close automatically ,when disappering that alert page need to get reload) |  | Fixed | Fixed in cloud
|  | 2.when we click modify approver icon ,its shows user selection popup in that user selection popup when we click save button its shows confirmation popup ( that confirmation popup shows wrong content) |  | Fixed | Fixed in cloud
|  | 3.when we click modify approver icon ,its shows user selection popup in that user selection popup when we click save button its shows confirmation popup, when we cancel or close that popup ,and again try to click modify approver icon its shows table alert popup |  | Fixed | Fixed in cloud
|  | 4.modify approver icon-- after modifying user its shows saved successfully alert , that alert need to close automatically & when disappering that alert page need to get reload |  | Fixed | Fixed in cloud
|  | 5.data not found issue when we modify approver in view log |  | Fixed | Fixed in cloud
|  | 6.let us assume, if we selected same cft user for both risk & feasibility sub forms, when we modify approver in view log both the subforms cft user get changed after that complete risk subform cft sign off ,, and then observe viewlog we have option to change cft user for feasibility subform when we change user for feasibility form ,already sign off user in risk form get changed. |  | Fixed | Fixed in cloud
|  | 7. data not found issue --- 2 times change cft user by using modify approver icon and on 3 rd time click on terminate icon |  | Fixed | Fixed in cloud
|  | 8. view log modify approver icon---- let us assume if we have selected user 1, user2 for cft sign off but now we have option to select both the cft user as same user as user 1 through modify approver icon ( need alert for that same user selection) |  | Fixed | Fixed in cloud
|  | 9.data not found issue - ,(let us assume 2 cft user for subform) if we modify cft user as initiator for both the reviewer section in view log. |  | Fixed | Fixed in cloud
|  | 10.if we change cft user through modify approver icon ,the department not getting changed |  | Fixed | Fixed in cloud
62 |  | Department Review ---action termination & modify approver
|  | 1.when we click terminate icon, confirmation popup not showing |  | Fixed | Fixed in cloud
|  | 2.when we terminate dept review, action is successfully terminated alert will display ,when we close that alert, page will get reload and on default it shows team sign off tab ( when the page will get reload it should show same dept review tab ) |  | Fixed | Fixed in cloud
|  | 3.once dept review completed and again send dept review for 2 nd time , in view log its over ride the 1 st dept review data's ( need to show both the records) |  | Fixed | Fixed in cloud
|  | 4.if we modify dept user for one subforms , whether the user in all other subforms also need to change like team sign off workflow..? |  | Fixed | Fixed in cloud
|  | 5.action is successfully terminated alert & saved successfully alert - not disappearing automatically and when alert get disappeared page need to get reload |  | Fixed | Fixed in cloud
|  | 6.we have option to select same user for dept review through modify approver icon , for that fiunctionality need to give alert |  | Fixed | Fixed in cloud
63 | actions | 1.action management - change management sub menu not showing | high | Fixed | Fixed in cloud
|  | 2.under change management when we try to open actions menu its shows access denied |  | Fixed | Fixed in cloud
64 | cft setup | MG vave records showing in change management cft setup ( note : fix already given) | medium | Fixed | Fixed in cloud
65 | view log | view log - sign off section loding | high | Fixed | Fixed in cloud