## APQP Known issue list
| Issue Description | Status/Comments
1 | For Edit charter (from draft ) added supplier is listed in charter and not ableto change the supplier using add supplier option.( | Working behavior
2 | Expand the supplier tree with multiple parts select one part from each supplier and add | Limitation as the supplier is not checked it is not possible to identify
3 | Supplier management portal not opening completed project on clicking notification icon | Fixed in dev not Integrated
4 | Downloaded documents showing deliverables as heading for documents | Not an issue
5 | Daily update mail is not sending on editing the existing periodic update data
6 | User Section in roles is not needed -Suggesting to remove | Not Feasible
7 | Supplier field given as mandatory in charter template and changed design for an existing project. On editing the charter it asks for Mandatory supplier alert and no provision to add supplier from charter
8 | Suite level user replacement is not updating the project owner of the project. Only the module and group rights assigned to selected user | User Replace icon given for admin
9 | Not able to delete a Phase havign deliverable with input document
10 | When Supplier user logs in Navigate section is showing by clicking my deliverable list menu. On swithcing the project from that page it is getting removed | Working behavior(Different view for PPAP and APQP project)
11 | When we map a project to a program the PM is assigned as one of the owner, but on unmapping the the project ownership not removed | Working behavior
12 | Once a project is selected on clicking back need to navigate to same listing screen page | Dave Review Point
13 | Mentor Comments popup need to show in maximized view- Add comments is not visible by default
14 | Mentor Comments email date is not in MMM format, need to make change in the contents
15 | Periodic update - The popup should be maximized by default, hard to update periodic update data in the popup.
16 | Position duplication in charter popup selection | Need to check
17 | UI/UX- New Issue Button Icon missing Messages- send button icon missing for Reply Forms- 1.Publish button icon missing 2. Done Button icon missing 3.Horizontal scroll showing which is not needed Document Viewer- Upload and done button icon in drag and drop popup missing-
18 | Need to remove Configuration from the landing page | Not Required
19 | Org chart widget view is not good, also not showing as per the project
20 | Project Creation date also needed in the listing screen
21 | When a milestone in converted to normal task the duration changed to .11 days | Not able to provide Tool limitation
22 | Import charter in supplier ppap is getting added in APQP projects | Fixed11202
23 | Phase % completion color is not showing always in the Gantt
24 | When Phase is set as predecessor it is showing at the time of entering and removign only on refresh | Need to check
25 | Charter page-Position popup is showign positions multiple times | Issue #16- Duplicate
26 | need to restrict multiple user selection from resourcemappign section(XML Import section)
27 | Project Ready to complete popup is not gettign closed on clicking complete button | Fixed in dev not Integrated
28 | Allowing to complete task with Additional document awaiting approval | TBD
29 | Template - Add template showing "Note: Dropdown values highlighted with blue are program " Alert which is not needed for templates
30 | 1. Expectation showing korean charaters 2. Expectation Scoring- Auto save needed 3. Rename add custom column 4. Allowing same score value multiple time 5. Serial Number should be non editable( now allowing to edit and save but got changed while adding new row, move up-down) 6.Not able to remove a checklist once linked with a deliverable 7. Allowing to delete a checklist from master even after linking( No depenedency alert) 8. Not able to remove score checks from deliverable info once mapped
31 | On attaching document with 200+ char it got saved on trying to delete getting undefined alert | Limit given upto 200 charracters only
32 | Immediate Predecessor option will get override (Husco Requirement) | Known Item
33 | Project Chart in gantt page header need to change as org chart as in the Widget
34 | Master template- When a template is mapped with other the the delay is showing for that task in the project
35 | Not able to delete meetings created in aproject | Raghu
36 | Position, Teams UI change in charter | Fixed in dev not Integrated
37 | Configuration-Creation date picker is clickable for the published Configuration- Make it as non editable
38 | Approval pending sort in listing screen is not working as expected
39 | Without assigning resource in deliverable info Automatic task completion on approval option is not working
40 | Schedule dates in the charter is showing nonedit icon in draft mode
41 | Baseline start and finish date are showing different time in show baseline
42 | Sporadic Issue- My gantt is not showing projects in the dropdown | Fixed in dev
43 | Not able to attach output usign the attachment icon if the grid comes in the 2nd line
44 | Notification alert is not closing based on business Rule Timing
45 | Master template- Showing error while creating a project using master template | Fixed in dev( Impact of the multi task/copy escalation item given for wipro)
46 | Charter form save alert is hiding behind so not able to see on scrolling up only we can see the alert
47 | Configuration-After baseline the alert for creating configuration is showing twice
48 | Roles - Not able to add competency in the charter before saving( working only for edit charter)
49 | Under supplier program when same project name is created then on 3rd similar project name it is showing error
50 | User with PM rights is not able to see the projects created by them in the widget
51 | Gate review in Program- When the gate review date is higher than the projects finish date then the GR is not showing in the timeline
52 | Project name with more than 100 characters are not showing in listing screen
53 | Allowing to save project name till 165 characters but only 100 is listing
54 | Need an alert if the project name is more than limit- now showing some error
55 | Part Family is not showing inside the Gantt page
56 | Undefined is showing under custom op folder colum in gantt page | Limitatiion
57 | When a template is mapped inside a template then days of delay is showing under notification
58 | Suggesting to include the template selected in Charter for program and inside supplier popup for projects
59 | When a supplier project name is given with / then it is accepting but on saving charter showing error
60 | Not allowing to create project When same project name is given form multiple projects while initiating a program
61 | Assigned a predecessor only for a phase (its subtask is not having any predecessor), then it allows to complete the sub task without any validation and hence the phase also getting completed.
62 | Need an option to remove checklist linkage, not allowing to uncheck the score value
63 | SM Import is allowing to create same partname with diff part number but for program import it shows duplicate part
64 | Should show all project Owners on hovering from the listing screen( now not showin all in case of more than 10)
65 | Suggesting to show an alert while switching from partially filled charter page that the entered data will lose. Currently it is redirecting to other page immidiately and losing the data
66 | Configuration document is showing PM name differently after adding new PM
67 | Approval pending program, when Project is added inside program charter is showing project inconversion in listing screen instead of showing approver name( Applicable only for project listing)

## APQP FST Integration
| Issue Description | Status
1 | Other owner is able to publish an Aqua/FST doc from deli info page - | Pending- Integration with other module
2 | User without FST admin is able to publish FST Doc | Pending- Integration with other module
3 | There is no validation to Attach/delete a PI to a project | Pending- Integration with other module
4 | For compelted task also FST linkage is possible | Pending- Integration with other module
5 | Allowing to atach same PI in a multiple projects | Pending- Integration with other module
6
7

## Sheet1
Emails | Status | mail subject
New Document Creation Mail | generated | NewDocCreation_Supplier PPAP Ver1
Delete Approver Escalation Mail | generated | Approver Escalation_Supplier PPAP Ver1 | Not removed after rejection
ProjectApprovedNotification | generated | PPLProjectApprovalNotification : Email Check 18th
ProjectRejectedNotification | Genereated | PPLProjectRejectedNotification : Email Check 18th
OpDocRejectionNotificationToTaskOwners | Genereated | PPLOpDocRejectionNotification Deliverable
PlanRejectionNotificationToProjectOwners | Generated | PPLPlanRejectionNotification Email Check 18th
PlanTerminationNotificationToProjectOwners | Generated | PPLPlanTerminationNotification Email Check 18th
PlanApprovalNotificationToProjectOwners | Generated | THLNotificationForApprover_Email Check 18th(Plan)
DocumentApprovalNotification | Generated | THLNotificationForApprover_Supplier PPAP Ver1
DeleteEsclationMail | Generated
Auto Approval Email was created (Project Creation) | Generated- but intterupted