## Sheet1
S.NO | PAGE | ISSUES | PRIORITY | REPORTED BY | DEV STATUS | QA STATUS | COMMENTS
1 | Report Date | Include all dates in the reports as per user preference | suggestions |  | Fixed | Fixed
2 | Action Item Status dropdown -ECR Form | Is it possible to indicate the status of actions as a dropdown insite the form | suggestions |  | Not required, since it impacts the workflow | Not an issue
3 | Change Checklist | 1.Need to corret spelling in the search and field name- Space and Caps L not needed (Checklist) | medium |  | Fixed | Fixed
|  | 2.Checklist search is not woring under assign checklist |  |  | Fixed
|  | 3. Scroll bar is not showing for assign checklist |  |  | Fixed
|  | 4. Department need to be site specific(Assign checklist) |  |  | Fixed
|  | 5. Department which is not assigned to any site also listed under assign checklist deprtment dropdown. |  |  | Fixed
|  | 6. Checklist created in the setup need to be site specific |  |  | Fixed
4 | non mandatory approver | 1.for nonmandatory approver workflow, form not closed after approvers approval , its in implemened status | medium |  | Fixed | Fixed
2.in view log, showing all the approvers ( not approved approver also showing with dates in view log)
3.for under view status ,approver not listing in approver section ( while opening from status page)
4.for 2 mandatory & 2 non mandatory approver --after CR approved,while opening CN from status page CR approver section showing 2 approved approver & CN approver section showing 4 approver
5 | project - by using assign approver | once project created with assign approver user, while publishing plan for APQP project,approval goes for category (old approver) only | medium |  | Fixed | Fixed
6 |  | 1.click on change category ,select position base routing | medium |  | Fixed | Fixed
2.initiate change request
3.then remove position base route & set default route as auto approval
4.again initiate change request
5.observe approver section
6.then publish the form and observe the changes(its showing position based routing popup)
7 | Documents to change - subforms | once external document added , not able to edit it on second time | medium |  | Fixed | Fixed
8 | CM Actions | Whether this menu is needed for a user who is not having CM group rights? | Suggestions |  | Not required | Not an issue
9 | Widget | CM Widget is showign all initiated CRs for a user without module rights | low |  | Fixed | Fixed
10 |  | Need to Remove publish from right click | Suggestions |  | Fixed | Fixed
11 | Multiple document selection need to be restricted in Documents subform | Multiple document selection need to be restricted in Documents subform | low |  | Fixed | Fixed
12 | Husco- | Approver is not showing in the form based on doc control group selection but the action item is sending to that user | low |  | Fixed | Fixed
13 | MG- PCR | Selected date is greater than the current date is getting for predicted date of deilvery(need future date) | low |  | Fixed | Fixed
14 | PCR-add document - link | in add document section ,after form get closed link is not opening(i.e: revision number & | Medium |  | Fixed | Fixed
attached document link)
15 | wavier & gabriel -change request status page | while giving special character in form, not able to open form from status page | Medium |  | Fixed | Fixed
16 | business rule | Evidence Document mandatory uncheck is not validating any of the pending actions from CN | low |  | Fixed | Fixed
1. Risk actions
2. Document Revision by Resp person
3. Project Completion
17 | wavier | while comments not given by approver ,its shows empty in form & for auto approval also comments showing empty in form | Medium |  | Not an issue | Not an issue
18 | Multi site-Brakepoint | CR Number editable in Brakepoint form | medium |  | Fixed | Fixed
19 | Multi site | Action item not showing for resp person- Blockage(corp user is given for action) Applicable for all forms | medium |  | Fixed | Fixed
Waiver approval Action, Team sign off also not showing
20 | PCR- cft sign off section | while we select cft members in setup for PCR but it follows the sub form cft sign off members,when sub forms submit & submit to team buttons clicked(NOTE: after refresh its shows correct) | low |  | Fixed | Fixed
21 | Overall sub form | Delay in saving data, especially in finance form | suggestions |  | Fixed | Fixed
22 | PCN Form Suggestion | Allowing to switch to Aqua yes no at a time after entering data - suggestign to give an alert or clear data on switching between checkbox | suggestions |  | Fixed | Fixed
23 | ECN | part name section need to lock (when part name is already selected in CR, we can able to change in CN also) | suggestions |  | Fixed | Fixed
24 | efectiveness tracker (multi site) | effectiveness tracker , not given as site specific | medium |  | Fixed | Fixed
| horizontal deployment (multi site) | horizontal deployment , not given as site specific | medium |  | Fixed | Fixed
25 | Usability- Part tree search | Part tree search is showing partially when clicked from left corner | Suggestions |  | Not an issue | Not an issue
26 | Horizontal deployment -Form | 1. PI selection popup in applicable product name should close automatically on clicking done. | Suggestions |  | Not an issue | Not an issue
2. Pi search is not working
3. Delete row option is needed for Blank Horizontal deployment form during initiation time itself
27 | doc pro | published risk form in doc pro , not showing full view | medium |  | Fixed | Fixed
|  | Disable cehckbox and text fields in feasibility form if there is no considerations added | Suggestions |  | Fixed | Fixed
28 | ECR & waiver - cn rejection | 1.cn rejected by approver | medium |  | Fixed | Fixed
2.open rejected cn from status page
3.click on revise document button
4.observe cn approver section(cn approver section shows empty but when click on publish , actions goes for particular approver)
29 | effectiveness tracker & horizontal deployment | not showing the CR full list based on closed status (NOTE : not replicating in 54 site) | low |  | Fixed | Fixed
30 | Manufacturign Feasibility Report | Need to lock Supplier code and name, allow to select ppap initiated date as past/current date | suggestions |  | Not an issue | Not an issue
31 | Copy Form | Target date for the CR form is not gettign saved | low |  | Fixed | Fixed
| copied risk form | action item not goes for responsible person | medium |  | Fixed | Fixed
32 | Sugesstion- Close CR | Suggesting for a confirmation message while closing CN using CLose button | suggestions |  | Fixed | Fixed
33 | cft rejection | when cft member reject the form without comments , in view log its shows waiting for signoff | medium |  | Fixed | Fixed
34 | CR rejection | 1.initiate change request | medium |  | Fixed | Fixed
2.publish CR form & reject
3.open rejected form from status page
4.click assign approver button
5.select approver as initiator & then publish
6.open CN from status page
7.observe cr & cn approver section (in cn section showing old approver name instead of newly selected approver name , but when click on publish action items goes for newly selected approver only)
8.& while opening closed PCN from doc pro ,CN approver section shows empty
35 | Design changes | all CM forms label and design changes | suggestions |  | Fixed | Fixed