## CM
S.No | Page Name | Issues | Priority | Responsible | Dev Status | QA status | Comments
1 | info content | whether info content for notify button , need to change as per michelin,,? | suggestion
2 | additional settings | category description - text box need to give as multi line | suggestion
3 | MG - project validation | for supplier user change request , when project is created and its not completed ,there is no validation when we click submit to team button | low
4 | MG - CFT rejection | 1.let us assume two CFT users( user 1 and user 2) in change request form, if one cft user (user 1) reject the form, then in view log its shows (user 2) CFT status as signed off | low
2.not able to open CR from status page -- change request closed by CFT Rejection scenario ( supplier login )
3.CN - CFT rejection ,,,is there any workflow ?
4.CN - CFT rejection,,, view log shows comments as "waiting for sign off " but already cft user selected rejected check box
5.let us assume two CFT users ( user 1 and user 2 ) , if one cft user ( user 1) reject the CN form, then form goes to closed status but in view log its shows ( user 2) CFT status as waiting for sign off
5 | risk setup | 1.once same data entered for two different category, if we make any edit it shows "already exists " alert | low
2.not able to make edit in low, medium, high risk section . it shows "parameter already exists" alert
6 | customer waiver approval | let us assume 4 users ( user1,user2,user3,user4)in customer waiver approval section, and the action item is submitted for approval, then login with user4 and open change request from status page , now for the user 4 checkbox are enabled in customer waiver approval section but there is no action item submitted for that user | suggestion
7 | mail | 1.reminder :notification for action item mail not removed from batch manager, even after action completion also | low
2.completion notification for action item mail not showing full content ( numbering format missing) - for Dept review
3.customer waiver approval - notification for action item mail - need to remove target date in mail content
4.rework escalation mail - need to change content and heading
5.change request rework - while opening hyperlink, whether need to show buttons ?
6.change request rework - reminder mail content showing twice ( for 2 nd round )
7.change request rework - esclation mail not generating
8 | husco workflow | 1.Standard workflow + document control group as select + category route | suggestion
2.Custom workflow + document control group as select + category route + ( assign approver not selected )
ISSUE: For this two scenario approval section shows empty
9 | doc pro - revision number link | published form in doc pro- revision number link is not clickable | low
10 | doc pro - documents | if we set initiator as approver for subforms, then published form in doc pro shows , approver check box as unchecked | low
NOTE : fix already given in 11204 hf
11 | doc pro - documents to change sub form | 1.publshed subform in doc pro - while opening attachments, its says "revision number linked with the document is not available" | low
2.revision number link is not clickable
12 | widgets | while opening approved, allocated, implementation status change request from widgets , its shows change request as PDF format with approved status | low
13 | documents - administrator actions | 1.documents ( administrator actions) - when we modify approval user in doc pro administrator actions, for that modified user view log shows terminated status also , need to remove that terminated status ( for Refer : screen shot attached) | low
2.in CN form approver section shows old approver only but we already changed new approver in doc pro ( administrator actions) , on clicking publish button action item goes for both new & old approver
3.when we remove all approvers in documents (administrator actions), change request getting auto approved but view log shows terminated status and approver section shows empty in CR form && when we publish CN, action item goes for category approver
4.documents (administrator actions) - when we add new approver in doc pro administrator actions ,with an existing approver , for CN approver section it shows old approver only but clicking publish button ,action item goes for both the user
5.set multiple approver in setup and initiate change request & publish it , then go to documents ( administrator actions) remove 1 approver and save it , while opening CN form its shows all the approver & view log shows terminated status also
14 | PCR form | while we select cft members in setup for PCR but it follows the sub form cft sign off members,when sub forms submit & submit to team buttons clicked(NOTE: after refresh its shows correct)---( moved from 11.2.0.2 hf old sheet) | low
15 |  | while clicking zip attachments link, form get loaded with blank screen | suggestion
16 | all forms - dropdown selection | 1. on multiple times selecting data's in drop down , its shows alert | Suggestions
2. Not allowing to select “select” option from dropdown once a value is selected applicable for all forms
17 | Risk Form | Target date picker is showing on the corner
18 | Documents to change | Document responsible person(PCR-Documents form) is not having access to view the documents attached for completing their action | Suggestions
19 | project - by using assign approver | once project created with assign approver user, while publishing plan for APQP project,approval goes for category (old approver) only
20 | Widget | CM Widget is showign all initiated CRs for a user without module rights | Suggestions
21 | widgets | 1. The widget data should show in some order either status based or CR # based | Suggestions
2. EVAV CR is not showing the status
3. Change request openign from EVAV widget is not having buttons inside form
22 | EVAV Landing | The EVAV CR widget showign deleted CR's too | low
23 | MG vave - cft login | MG Vave - if same cft user mapped for multiple sites, then while opening cft user through vave idea status page ,it shows count mismatch | low
24 | subforms | Responsible person action - for subforms if we assign multiple action item for same user,on completing single action item not able to submit | low
ISSUE: if we assign multiple action item ,during action completion time it not validating that particular action item , now it validating all the action item
25 | doc pro - published risk assessment form | while opening published risk form in doc pro, it not shows full view | low
26 |  | 1.Allowing to select same user in change coordinator and CFT section,, is that ok ? | Suggestions
2.department review popup - for change coordinater department section shows empty,, is that ok ?
27 | widgets | SM - change request widgets : listing change management records | low
28 | Business rule | business rule - enable / disable option not getting saved for both the clicks ( enable/disable) | low
29 | position based route | 1. 2 position route in single round scenario -- after the route get saved its shows route listing wrong and in form also approver section listing wrong. | medium
2. 1 st round position route & 2 nd round position route scenario --- in Route maping popup its shows same approver route for both the rounds and while making edits in one round other round also get changed
3. 1 st round position route & 2 nd round normal user --- route maping popup listing wrong and in form also approver section listig wrong
4. single round ,both position route & normal user ---in form approver section listing wrong ( position route popup what need to list ?)
30 | user rights - Gabriel | if user is deleted in suite, deleted user already maped in cross functional team setup not get updated | medium
31 | APQP project | if change request is initiated with APQP project , then delete created project in APQP , after that while opening project from change request status page its shows blank page | suggestion
32 | CR initation from PPAP as supplier user | When supplier user initated a Change request from PPAP project it is not getting added inside their status | suggestion
33 | Supplier project Creation | When a supplier initiates a change request, and created a project for that then the newly created project is showing only one SQE as project owner | suggestion
34 | Supplier management Workflow- Supplier user initiation | Restrict the view of other supplier users in the user selection popup for all areas | suggestion
35 | ECR form - include other document section | include other document section -- Revised document name section showing default document after publishing CR form | low
step 1: initiate engineering change request form
step 2: navigate to include other document section
step 3: add document from doc pro
step 4: publish the form and approve it
step 5:open CN from status page
step 6:navigate to include other document section & observe revised document name section
36 | MG - closed status - include other document section | closed status - revision number not opening in include other document section | low
NOTE: Fix already given in 11202 hf
37 | business rule- reject CR on team sign off - enable | let us assume 3 cft user in change request- if 1 st cft user reject the form , status changed to rejected. | low
Issue : 1.view log - shows waiting for approval " for 2 nd, 3rd cft user with modify approver, terminate icon
2.action item not removed for 2 nd, 3 rd cft user
3.Disable reject CR on team sign off ( ECR form)- if cft user click on no check box , then in view log status showing as rejected ,, is that ok?
38 | EV- AV change request widgets | EV-AV change request widgets need to show site specific data ( now showing all sites together) | low
39 | non mandatory approver - Business rule | non mandatory approver business rule enabled in business rule setup but published form in doc pro ,not showing non mandatory approvers | low
40 | copied MG sub supplier form | 1.check list section not showing copied form data | low
2.sign off section showing users based on current setup ,,, Is that ok ?
3.whether include other section data need to get copied..?
4.evidence section - remarks data not get copied
41 | copied MG forms | closed status - while clicking copy form button, form reload with all the buttons on top left corner, but while opening from status page its shows only MG specified buttons | low
42 | copied forms | 1.map template and numbering format | low
2.initiate change request and approve it
3.remove template and numbering format in the setup
4.navigate to status page and open closed status form
5.click on copy form button
issue : now alert is showing " There is no data for creating the form " , need to change that alert as per the working behaviour
43 | copied ECR forms | 1.include other section data not getting copied | low
2.action item section- comments also getting copied
3.ECN -dimension section remarks, evidence section remarks not getting copied
44 | non mandatory approver | 1. let us assume 4 user ( user 1, user 2, user 3, user 4) | low
2. set non mandatory approver route ( user 1, user 2 as Mandatory & user 3 , user 4 as Non mandatory)
3. login as user 1 and initiate change request and publish it
4. login as mandatory approver and approve it
5. open change request from status page
6. observe CR approval section
NOTE : Same scenario applicable, if we set initiator as non mandatory
ISSUE: On default Rejected check box getting checked for Non Mandatory approvers user 3 and user 4
45 | non mandatory approver | 1. let us assume 4 user ( user 1, user 2, user 3, user 4) | low
2. set non mandatory approver route ( user 1, user 2, user 3 , user 4 as Non mandatory)
3. initiate change request and publish it
4. login as any one approver (user 1) and approve it
5. open change request from status page
6. observe CR approval section
NOTE : Same scenario applicable, if we set initiator as non mandatory
ISSUE: On default Rejected check box getting checked for Non Mandatory approvers user 2 ,user 3 ,user 4
46 | subforms | subforms- some times while clicking submit button, it not shows submitted successfully alert | low
47 | deleted user | 1.create new user and assign all cm rights & cm integerated modules rights | low
2.perform some activities under created user
3.delete that user
4.Again create same user and assign rights
5.perform some activities under that user
ISSUE: actions item not getting for deleted user
48 | view log - dept review | if change request is closed without completing dept review action item then in view its showing as waiting for approval in status section, need to change the status | low
49 | Risk / Feasibility sub form, MG forms | Date section is editable for cft sign off user action item | low
50 | CN Rejection - multiple approver | 1.Map multiple approvers ( user 1, user 2) against category | low
2.initiate change request and approve it
3.open CN from status page
4.publish cn form
5.login as cn approve ( user 1 ) and Reject it
6.open view log from status page, observe cn approver section
ISSUE: CN approver section shows both Terminated and rejected status , record shows terminated by initiater
51 | Multi site reports | Approver wise change request report - approver section shows empty for category approver | low
52 | Route | 1.Create new route in setup | low
2.map created route against category
3.Delete created route
4.Refresh and observe the deleted route against the category
5.initiate change request
6.observe approver section
ISSUE : 1. Remove icon not get removed in change category section after the route get deleted
2.Approver section shows empty in change request form
53 | customer waiver approval setup | Designation get saved without selecting Approver. (scenario for existing record : without selecting approver we can save different designation for the particular record ) | low
54 | TDR form | add associated TDR'S link - multiple records selection in multiple pages not getting saved | low
(note: now current page records only getting saved)
55 | mails | 1.Need line space after dear all | low
2.need line space after mail content
3.remove line space after regards
4.dear all , need to change when mail trigged for single To address
56 | dept review mails | scenario : add multiple department & same mail id for different user | low
issue : 1.reminder mail To address got duplicated
2.esclation mail - user got duplicated in Tabluar column
57 | MG -VAVE | auto populated contact number not generating in vave idea form | low
58 | Report | 1.Reject CR on team sign off - Enable: if change request get rejeted by cft user, then rejected date not getting updated in reports | low
2.Approved status: request closed date showing in reports , scenario: if we select date in request closing date section in form
59 | pcn form- risk & feasibility subform responsible person action count | without clicking submit button ( once we enter target date and responsible person, the count will show in pcn ) | low
60 | document subform | pdf file format not opening from revision number link | low
61 | subforms - responsible person action item | 1.open responsible person action item | low
2.select target date / output attachment
3.click on submit button
ISSUE : after clicking submit button, we can able to edit data's in subform ( note : after clicking submit button, need to close that page automatically )
62 | document subform | 1. map document,responsible person, planned date in document subform | low
2.click on submit button
3.refresh the form
4.open document subform and select particular row ( data filled row )
5.delete that row by using right click delete
6. try to publish the CN form
ISSUE : on clicking publish ,its shows " There are some pending action " alert. but there is no pending action , we already delete that row in form
63 | mail - default notification to user | Default notification to mail not working--for selected user | low
64 | mail - link | while clicking mail link , its shows session expired alert | low
scenario : There is no active session in the browser
65 | business rule - husco workflow | document control group route dropdown selection, not showing other modules routes- when enable all module routes business rule is enabled | low
scenario: once we log out and log in , then other module routes showing
66 | view log- sign off tab | submitted on date not showing in view log for risk sign off | low
67 | michelin | info button content for associated tdr | low
68 | closed status form |  | low
closed status form (scenario : without doing any activities in subform )
1.document to change subform - all data sections are editable
2.validation subform - process, parameter,attachment - sections are editable
3.Feasibility subform- check box, attachment, action,target date, responsible person - sections are editable
4.finance subform - change details,lead time, peneteration,all data sections are editable
5.breakpoint subform - all data sections are ediable
69 | doc pro | once change request got deleted, whether that change request related document also need to delete from doc pro ? | suggestion
70 | business rule | new business rule page - need customer specific terms | suggestion
71 | status page | status page search - need to include deletion inprogress status in search dropdown | suggestion
72 | ECR form | need to lock extra row under approval section | low
73 | mail | 1.Change Management - Request is approved and Project created-- while opening form from hyperlink,need to show read only format | low
2.Change Management - Final Sign Off by Team---while opening form from hyperlink, whether need to give as read only format ?
74 | attachment | 1.initiate change request & navigate to present process attachment section | low
2.attach attachment
3.reload the page
4.click on attachment in present process section
ISSUE: Attachment popup not showing after refresh
75 | department review popup | without selecting department we can able to click save button, suppose user forget to select department and try to click save button need "alert" in that scenario | low
76 | Subform resp person action submission | After submitting to team the submit button is removing from subform only after url refresh
77 | Change request approval | approver section shows empty, while opening first time action item in change request approval action ( for subforms ) scenario : 1 st publish subform and then main form | low
78 | TDR | 1.Approved status - while opening view form link in associated TDRs section , there is no response | low
2.doc pro - not able to open attachment link, view form link in published form
79 | validation subform | for CFT user login - designation and department sections are editable | low
80 | cr form setup | Template mapping popup- Not applicable check box need to show , when all the forms for respective template is in inactive status | low
81 | cr form setup | Template mapping section- on clicking map template, its shows data tables alert popup, when all the forms for respective template is in inactive status | low
82 | change setup - actions | Vave idea category listing in action setup - change category popup selection | low
83 | Horizoontal deployment | search not working in PI selection popup | low
84 | view log | waiting for approval text need wording gap | low
85 | view log | when main form get terminated- view log approver section shows wrong user ( instead of approver name , now showing initiater name ) | low
86 | cr form setup | 1.need to remove subforms in main form template mapping section | low
2.need to remove cn forms in main form template mapping section or by default cn form should show status as inactive in new/edit template
87 | Risk, consideration, document to change setup | step 1.open existing record | low
step 2.click on save
ISSUE: it shows alert as " already exists " but actual alert we need is "saved successfully"
88 | team sign off | 1.initiate change request | low
2.assign 4 user in team sign off section
3..without selecting target date , submit team sign off action item
4.navigate to view log and terminate 3 action item
5.login as responsible person and complete sign off action item
6.open change request form from status page
7.naviagte to team sign off section
8.try to select target date
ISSUE: Target date section is editable for requester ,whose action item is terminated in view log
89 | validation subform | validation numbering format section editable , need to lock that section | low
90 | customer waiver approval | For customer waiver approval responsible person login - approved by,designation fields are editable | low
91 | TDR | need to restrict high priority, project, part name section in status page for TDR workflow | low
92 | CFT setup | 1.search active status record | low
2.click on remove icon
Issue: while clicking remove icon no response but after refresh record got removed
93 | streling form | 1.document to change section - document name section is editable , need to lock document name section | low
2.action item section is editable, need to lock
3.Target date not getting saved for cft - added by right click add functionality
4.include other document action completion not validating during CN publish
94 | document subform | right click add functionality - actual date is editable for Requester ,need to lock actual date section | low
95 | CR Form setup | 1.new/ edit template - while making active and inactive status ,its shows wrong alert | low
2.copy designer button Not working for second time selection
3.create multiple copy of same template and then after delete one copied template ISSUE : on deleting single template all the copied template geting deleted
96 | mandatory change title - enable | on clicking close icon in change request popup, it take time to show confirmation popup | low
97 | customer change request form | PCN- team sign off and review log label missing | low
98 | widgets | Given Change requst group rights to a user, Initated a change request-> Removed the group rights-> Expanded the CR widget from landing page-> Status page shows loading (Search builder) | low
99 | sign off section | 1.remove subform additional settings | low
2.initiate change request
3.observe main form & subform cft user
4.replace user in multidisciplinary section
5.refresh the form
6.observe main form & subform cft user
ISSUE: when we change user in multidiscplinary section, that changed user not reflecting in subform cft section
100 | pending action popup | pending action popup - top popup header shows empty | low
101 | mail | high priority change request mail - main & subform approvers address missing in TO address | low
102 | APQP | source ref. not generating , if we initiate change request from APQP | low
103 | sub form additional settings | Select folder for documents label need madatory symbol | low
104 | All sub form | need to give Target date selection as mandatory for responsible person action | low