## Sheet1
| Issue Description | Status/Dev Comments | Status
1 | For Edit charter (from draft ) added supplier is listed in charter and not ableto change the supplier using add supplier option.( | Working behavior- for projects edit given for program | Closed
2 | Expand the supplier tree with multiple parts select one part from each supplier and add | Limitation as the supplier is not checked it is not possible to identify | Closed
3 | Supplier management portal not opening completed project on clicking notification icon | FIXED- Working in 1130 | Closed
4 | Downloaded documents showing deliverables as heading for documents | Not an issue | Closed
5 | Daily update mail is not sending on editing the existing periodic update data | PENDING | Open
6 | User Section in roles is not needed -Suggesting to remove | Not Feasible- Dependancy with the user selection inside the popup | Closed
7 | Supplier field given as mandatory in charter template and changed design for an existing project. On editing the charter it asks for Mandatory supplier alert and no provision to add supplier from charter | Work Around, supplier can be added from Gantt page and that will list in charter aswell. Then the user can save the charter( Verified in 1130- Apr2nd) | Closed
8 | Suite level user replacement is not updating the project owner of the project. Only the module and group rights assigned to selected user | User Replace icon given for admin | Closed
9 | Not able to delete a Phase havign deliverable with input document | Fixed in 11204 | Closed
10 | When Supplier user logs in Navigate section is showing by clicking my deliverable list menu. On swithcing the project from that page it is getting removed | Working behavior(Different view for PPAP and APQP project) | closed
11 | When we map a project to a program the PM is assigned as one of the owner, but on unmapping the the project ownership not removed | Working behavior | Closed
12 | Once a project is selected on clicking back need to navigate to same listing screen page | Dave Review Point (Given in1130) | Closed
13 | Mentor Comments popup need to show in maximized view- Add comments is not visible by default | Assigned to Devan | OPen
14 | Mentor Comments email date is not in MMM format, need to make change in the contents | 18/Aug/2023- Date format fixed | Closed
15 | Periodic update - The popup should be maximized by default, hard to update periodic update data in the popup. | Assigned to Devan | Open
16 | Position duplication in charter popup selection | Fixed | Closed
17 | UI/UX- New Issue Button Icon missing Messages- send button icon missing for Reply Forms- 1.Publish button icon missing 2. Done Button icon missing 3.Horizontal scroll showing which is not needed Document Viewer- Upload and done button icon in drag and drop popup missing- | PENDING | OPen
18 | Need to remove Configuration from the landing page | Not Required | Open
19 | Org chart widget view is not good, also not showing as per the project (project name header is mising ) | PENDING | open
20 | Project Creation date also needed in the listing screen | PENDING | Open
21 | When a milestone in converted to normal task the duration changed to .11 days | Not able to provide Tool limitation- New UI it is not showing like this | Open
22 | Import charter in supplier ppap is getting added in APQP projects | Fixed11202 | Closed
23 | Phase % completion color is not showing always in the Gantt | Not able to replicate in 1130 | Closed
24 | When Phase is set as predecessor it is showing at the time of entering and removign only on refresh | Phase can be given as predecessor( verified in 11version Old UI) Phase as predecessor is Not applicable to new UI | Closed
25 | Charter page-Position popup is showign positions multiple times | Issue #16- Duplicate | Closed
26 | Import Project using XML:-Need to restrict multiple user selection from resourcemappign section(XML Import section) Add new resource in Gantt page:- Need option to desect the user from user selection popup | Not applicable_Limitation | Closed
27 | Project Ready to complete popup is not gettign closed on clicking complete button | Fixed in 11203 | Closed
28 | Allowing to complete task with Additional document awaiting approval | TBD | OPen
29 | Template - Add template showing "Note: Dropdown values highlighted with blue are program " Alert which is not needed for templates | Assigned to Vaibhavi | open
30 | 1. Expectation showing korean charaters 2. Expectation Scoring- Auto save needed 3. Rename add custom column 4. Allowing same score value multiple time 5. Serial Number should be non editable( now allowing to edit and save but got changed while adding new row, move up-down) 6.Not able to remove a checklist once linked with a deliverable 7. Allowing to delete a checklist from master even after linking( No depenedency alert) 8. Not able to remove score checks from deliverable info once mapped (shows Undefined alert) | PENDING | open
31 | On attaching document with 200+ char it got saved on trying to delete getting undefined alert | Limit given upto 1000 charracters in 1130 | closed
32 | Immediate Predecessor option will get override (Husco Requirement) | Known Item- Applicable in New UI | Closed
33 | Project Chart in gantt page header need to change as org chart as in the Widget | Assigned to Vaibhavi | Open
34 | Master template- When a template is mapped with other then the delay is showing for that task in the project | FIXED in 1130( NEW UI) | Open
35 | Not able to delete meetings created in aproject | Raghu | open
36 | Position, Teams UI change in charter | Fixed in dev not Integrated | closed
37 | Configuration-Creation date picker is clickable for the published Configuration- Make it as non editable | Not an issue | closed
38 | Approval pending sort in listing screen is not working as expected | Not replicating | closed
39 | Without assigning resource in deliverable info Automatic task completion on approval option is not working | Addressed along with Lucid phase 2 items | Closed
40 | Schedule dates in the charter is showing nonedit icon in draft mode | Fixed in dev DEVAN | Open
41 | Baseline start and finish date are showing different time in show baseline | Fixed in 11203 | Closed
42 | Sporadic Issue- My gantt is not showing projects in the dropdown | Fixed in dev- Not replicating in 1130 | Closed
43 | Not able to attach output usign the attachment icon if the grid comes in the 2nd line | Limitation- Need to check | Open
44 | Notification alert is not closing based on business Rule Timing | FIXED In 1130 | Closed
45 | Master template- Showing error while creating a project using master template | Fixed in dev( Impact of the multi task/copy escalation item given for wipro) | Closed
46 | Charter form save alert is hiding behind so not able to see on scrolling up only we can see the alert | Assigned to Devan | open
47 | Configuration-After baseline the alert for creating configuration is showing twice | Assigned to Devan | open
48 | Roles - Not able to add competency in the charter before saving( working only for edit charter) | Working Behaviour need to make changes based on customer requirement | Closed
49 | Under supplier program when same project name is created then on 3rd similar project name it is showing error | Fixed | Closed
50 | User with PM rights is not able to see the projects created by them in the widget | Showing in 1130- Not replicating | Closed
51 | Gate review in Program- When the gate review date is higher than the projects finish date then the GR is not showing in the timeline | Sporadic- Able to view some times based on screen resolution | OPen
52 | Project name with more than 100 characters are not showing in listing screen | Limitation, can view only 100 | Closed
53 | Allowing to save project name till 165 characters but only 100 is listing | Assigned to Devan, Now allows more than 1000 | Closed
54 | Need an alert if the project name is more than limit- now showing some error | Error fixed, Still shows 100 characters only | Closed
55 | Part Family is not showing inside the Gantt page | Pending | open
56 | Undefined is showing under custom op folder colum in gantt page | Limitatiion | open
57 | When a template is mapped inside a template then days of delay is showing under notification | Duplicate Issue #34 | OPen
58 | Suggesting to include the template selected in Charter for program and inside supplier popup for projects | Sheet2!A1 | TBD
59 | When a supplier project name is given with / then it is accepting but on saving charter showing error, Applicable for project charter | FIXED IN 1130 | closed
60 | Not allowing to create project When same project name is given form multiple projects while initiating a program | Fixed in 11206( Auto increment value given in project name) | closed
61 | Assigned a predecessor only for a phase (its subtask is not having any predecessor), then it allows to complete the sub task without any validation and hence the phase also getting completed. | Restricted predecessor for phase(reopen in 1114 and 1130) | Open
62 | Need an option to remove checklist linkage, not allowing to uncheck the score value | will handle based on the priority | open
63 | SM Import is allowing to create same partname with diff part number but for program import it shows duplicate part | TBD | TBD
64 | Should show all project Owners on hovering from the listing screen( now not showin all in case of more than 10) | FIXED IN 1130 | Closed
65 | Suggesting to show an alert while switching from partially filled charter page, as there is no auto save the data entered is lost and the user need to reenter everything again | Fixed in 11205 | closed
66 | Configuration document is showing PM name differently after adding new PM | new PM name showign now | closed
67 | Approval pending program, when Project is added inside program charter is showing project inconversion in listing screen instead of showing approver name( Applicable only for project listing) | Limitation | TBD
68 | Date field in the charter is showing red icon instead of hand symbol during selection, (screen shot in sheet 2) | Pending | open
69 | Email- For the Rejection Charter email Comments are not getting | FIXED IN 1130 | Closed
70 | Archived a project and deleted the pillar. On unarchive the project is not showing in the listing page | FIXED IN 1130 | Closed
71 | When We archive a project, It is allowing to delete the pillar associated with it. Need to allow pillar deletion only if the project is deleted. | FIXED IN 1130 | Closed
72 | Button icon missing for session expiry popup | Pending | OPen
73 | Save charter as Draft, Now mandatory fields are required to save as draft. Need limited validation for draft | Suggestion | TBD
74 | 2 locations are there in the SM portal for a supplier, Removed one from the portal but in charter add supplier tree is showing both addresses | Not replicating in 1130 | Closed
75 | Suggestion My Gantt-For a document pending for approval, mand op the alert is not getting on updating 100 % from gantt page | Not Replicating
76 | My Gantt-for supplier projects the navigate section(Icons) is not there . | Fixed in 11204 | Closed
77 | PSW- If an interim approval is set, then also the system allows to complete the project without validating the pending qty committed based on the expiry date | TBD | TBD
78 | The gantt page timeline is not alligned on changing the working hours | Not Replicating | Closed
79 | WBS in doc viewer shows 0 | Known issue- Limitation | OPen
80 | Include Supplier/Part details in the Project Archive list also Include date search option | Not in priority | open
81 | Suggesting to include Deletion confirmation alert for all delete options | limitation is there for constraints | Open
82 | Planned vs Actual dates are not showing based on the shift time | Fixed in 11203 | Closed
83 | Suggesting to include a hyperlink in the project constraints popup from the gantt page to redirect to dependent project | Not in priority | TBD
84 | Project Completed is not able to close using bell icon | Fixed in 11203 | closed
85 | Attachments in del info- 1Attach a local input doc then click on forms/doc attachment button 2. close without attaching any doc 3. Click on add button 4. Check for place holder alert 5. Add same document again from local 6. Getting placeholder alert on clicking add. Note: If we try to attach a differnt document from local it is allowing to attach as input |  | open
86 | When constraint is enabled then it is not allowing user to attach 2nd rev documnet | Fixed in 11203 | closed
87 | Critical path icon needed for my gantt?- Need to remove | Not required | closed
88 | Milestone, Scoring and expectation Scenario( Effort based) 1. For a project keep the milestone task as uncompleted and complete rest of the tasks, thenoverall % shows 100 and allows user to complete from charter but it will not show from notification bell icon. 2. Scoring- Linking checklist for a task in a project or phase with single task then the % completion is not updating in listing screen. 3. Templates page->Checklist tab->Save successfully alert is hardcoded |  | open
89 | Convert project from template, import xml - The project should be under draft status and on opening charter the Custom op folder section is disabled. | Fixed 11204 | Closed
90 | Excel import is not working while attachign from a draft project | Fixed 11204 | Closed
91 | On Periodic update the hours field is mandatory, once we close the alert it automatically taken 0 as hours and getting updated.( is this correct?) | Working behavior | Closed
92 | Predecessor alert is not showing while updating progress % under my gantt | Fixed 11203 | Closed
93 | Published Configuration External Document is not opening from the link | Fixed 11203 | Closed
94 | XML import- The scheduled dates updated in the charter is not considered for the project planning | Working behavior | Closed
95 | Automatic Task Completion on approval doesn’t consider Constraints | Working behavior | TBD
96 | When there is no pending projects then on navigating from my gantt menu it shows no projects assigned page | Fixed 11204 | Closed
97 | Multisite projects are showing in the add projects under program and Add constraints | Fixed in 11206 | Closed
98 | Project Created under program shows Supplier primary contact as PM even if program is created by SQE | Working behavior | Closed
99 | Lucid- Project completion on all task is not handled for Markon track % udpate | Next release-plan | open
100 | Export to excel from Gantt page- | Fixed 1130(special character and number combination issue reported) | OPen
101 | Copy Project- Supplier project copy is not applicable as the edit charter of project doent show add supplier option | LIMITATION | Closed
102 | Add supplier popup in charter- Not able to search the template | Fixed 1130 | Closed
103 | When the task is automatically aligned or repositioned then the tasks are not getting copied in the current gantt order |  | TBD
104 | When a PSW document is attached for review and then send for approval- the document name doesn’t include project name as prefix in the actionpage |  | Need to check
105 | Suggesting to show save successfully alert on enabling or disabling BR toggle button |  | open
106 | Disable add button after document attachment . Now allowing multiple clicks and duplicate doc getting attached in del info | Next release-plan(11206) | closed
107 | Gate Review Page update | 1130 | closed
108 | Add new resource in Gantt page- Need option to desect the user from user selection popup | Not Applicable(option is there to deselect user from the dropdown list) | closed
109 | Review Page Publish- Allignment not good, Progress bar graph will not be listed in the publised view | Limitation | Closed
110 | MDR setup- Combine % and date for review process | Chad Requirement | Open
111 | Scoring integration with Audit Checklist | Chad Requirement | open
11205( Aug 2023)
112 | Program view - On clicking deliverable list from charter page program tree view is missing(Scenario-Enable Advance program view in BR) |  | Closed
113 | For a project created from EVAV platform with supplier , then when a task is assigned to supplier contact they are not able to see the project from My gantt. ( Supplier user is having access only for SM platform) | Need to provide evav rights also to the SM user, check with suite team | closed
114 | Program /Project manager field name should rename to Project/Program Owners in Project Information popup from Gantt page |  | Need to check
115 | Program/Project manager change option in charter- After changing and publishing charter the PM is not getting updated. | Not replicating 1130cy0 | closed
116 | Admin user is able to edit the deliverable name of project of other owners | Handled in1130 | Closed
117 | Program Gantt View, the slider design is not alligned, border showing outside the line | sporadically showing | open
118 | When a supplier project is archived, then it is not removing from program charter. When trying to add the same supplier part in the program it is not getting added . | Planning to provide in Future | open
119 | When a part is mapped in a program and then saved as draft, on creating new program with another part then there will be 2 projects created with same part | After Adding new part delete button shows and PM can delete the part and continue | Closed
120 | Bug Fix- Not allowing to add resource in a project with one Milestone task under a phase | Fixed given in 11206HF | Closed
121 | % is not updating based on Deleting document | Fixed given in 11206HF | Closed
122 | Program Ownership rights not needed for sub project owners | Fixed given in 11206HF | Closed
123 | Constraint is not considering for task completion when document is attached and aproved | Duplicate Issue #95 | OPen
124 | When Custom folder is created incharter, then on renaming project name the Customer folder name got changed in docpro | Working behavior | Closed
125 | Terminating a draft converted document, is not removing the comments given during document attachment |  | Open
126 | Deleted a task with input document from the gantt page but the document is not getting removed from docpro |  | Open
127 | Approved Date field showing data in awaiting approval status in the revision history popup. Need to update the field title accordingly | Duplicate Issue #95 | TBD
128 | Copy Project-Scheduled finish date is showing one day less that start date in the published charter( awaiting approval charter too) | Not replicating Next release plan | Closed
129 | Not allowing to attach multiple additional documents from local usign ctrl select | Fixed in dev Next release plan | Closed
130 | Without entering Input name it is allowing to attach documents for Docpro, Local, Url, Forms etc.. | Fixed 11207 | Closed
131 | The resource mapped in the task against a checklist/form cannot be removed from del info page | Next release plan | Open
132 | When a document is rejected then the NEXT approver status shows as terminated with the comments of previous approver in revision history | Working Behavior | closed
133 | The revision history doesnt show the document awaiting approval status( shows like there is no valid revision available), Only the deliverable info opens the awaiting doc | working behavior | closed
134 | Multi select and attach additional document is not working. Only one document getting attached | Fixed in dev- release plan after 11208 | Closed
135 | Project prefix- Business rule- Showing null in the gantt page for project selection if the preference is not set | Fixed 11206 | Closed
136 | The Project created with multiple site selection in charter is not showing in the other site The Projects menu is not showing by default for the resource added in multiple site project, need to provide rights manually to show the menu. Till that time unable to navigate to my gantt page | Given in 1130 | Closed
137 | Project charter saved with approval for 2nd revision, before completing approval again saved the charter with charter route, Then Published the plan. | Charter showing 1st route for approval, Plan showing 2nd route for approval | TBD
138 | Copy Project- Custom column header is showing as CC1, CC2 … the name given in actual project is not showing. Data is populated |  | Open
139 | When a mentor is added in charter with pillar approval , Approval action is going to the user added in the pillar BR only. User added in charter is not showing in listing aswell as review page | Working Behavior | closed
140 | Date mismatch in the project listing screenShowing one day less than charter date |  | Closed
141 | The resource is able to select Periodic update against a phase, but on saving it shows error | Phase wise periodic update is not recommended | open
142 | When Mentor is assigned in pillar , it is not showing in the charter sometimes | Sporadic issue | OPen
143 | URL attachment- Will not send for approval, Count will update in listing screen but Progress% is not applicable | Working Behavior | NA
144 | Aqua, FST document will not go for default project manager approval | Limitation | closed
145 | Resource Allocation- 1. Suggesting to show the project details based on the resource selection made in the bottom of the popup 2. If the resource allocation is partial then it should show the time on hovering the task load |  | open
146 | When a document is approved after draft Review in the Gantt page it Is showing as NA in the approval status | not replicating in 1130 | closed
147 | MDR- The document Viewer Ontime rating is showing based on task completion, but in deliverable info it will take based on rating scale value by the reviewer | Enhancement for MDR is in pipeline | TBD
148 | Revision History-Sugesting to change Approved date field name as awaiting approval, rejected status details also listed there |  | open
149 | Document viewer Published form is showing approver column. Whichi is removed from doc viewer page |  | open
150 | Advance program-Yes the supplier view is showing with project details | Not an issue | closed
151 | On converting template to project From SM when the name of a project from EVAV platform is given then system showing error | 1130-Fixed | Closed
152 | When a supplier user mail id( primary/sec)is updated in the supplier details page then for project created with that supplier will not get updated, Need tomanually replace the user from gantt page to show action /tasks for the new login | Working behavior | Closed
153 | Supplier management emails are showing under APQP in Batch manager- sugesting to show in SM portal | Not possible as it is generating from APQP | Closed
154 | Supplier tracking matrix report is not needed in access rights( Groups) | Removed in 1130 CY1 | Closed
155 | When a part is linked in a project mapped with program, program doent show the part details. Multiple porgrams may have same project so not able to handle it. | Limitation
156 | Emails Corrections |  | Closed
Project completed- Content need to modify with Regards and break line
Task Assigned ,Task Completion - Project Manager , New Program Created ,Task Revised - ,Space need after the link
Task Escalation - Scheduled date spelling incorrect, Mail is addressing to PM twice
Document Creation Notification - Header footer not avail(Task owner to project Owner)
Project Created under Program,- Line break needed for the contents( applicable to almost all mails) and space needed after link
Mentor mail content is duplicate
Project Completed- Content modification, line brk needed
157 | User with admin rights is able to delete and archived project of other owners without any intimation- Need to restrict this | TBD | OPen
158 | Review page is not showing status other than not started under deliverable summary after 10th row | not a priority item | open
159 | Supplier user is getting project view accesss- Scenario the view access got enabled for a particular user and on resaving the group rights it is working fine | Reported by Lucid, Not replicated in local | closed
160 | Status filter is not working in issue set up page( All tabs) | Pending | open
161 | Attached additional doc as resource and sent for approval, approver rejected document, PM deleted the document, Approver approved deletion request. Document got deleted but % not changed to 100 | Fix given in1130 | closed
162 | Multi site Widget- Showing project created in Corporate in the multisite widget on selecting the PI | need to restrict PI listing | open
163 | Allowing to complete task on approving document even after the constraint is enabled | Pending | open
164 | Special character named project on docwnloading to excel is not showing name properly | Pending, checked but having some issue to fix it
165 | Grid View, When lengthy text is given in Checklist then the grid is showing only + Symbol in default view. Sugesting to show wrap text view in the listing screen itself. Same applicable to the bulk approval for lengthy doc name | Pending | open
166 | Gate review- When a document attached against a gate review and is awaiting for approval ,it is allowing to approve GR task without consideting that attachment |  | open
167 | Six- Sigma template- On mapping to a project showing mismatch in phase structure | Need to correct in the db, Workaroung- savethe template once before using in a project | Open
168
| Landing page Changes |  | Open
1. Org Chart widget in the landing page should show as in the project Gantt view
2. Configuration Widget showing based on the timeline view
3. EV AV Meetings widget is showing old meetings too.
4. Risk and Meetings widget need to show data for the assigned team members also.
5. Project widget is not showing the project created by PM(without module rights)
6. Suggesting to show the listing in some order
SM: Widgets Not loading data in todays task+overdue
| SM:Supplier PPAP blank | Applicable to SQE/SQM, but for them new landing page is given
Project Widget for New Gantt UI is showing icons , Alignment not good
1. Deliverable Priorities need to move from Project Management to Setup Section
2.(Groups-> Project Charter need to rename as Charter Template and if needed can be move to Setup Section since it is showing under Project Setup page
| 3. Supplier Tracking Matrix need to remove from Reports section | Done in 1130
4. THL need to remove for "THLCriticalPath" and "THLFeverChart"
5. Need to remove APQP_ from "APQP_ApprovalChart", "APQP_OnTimePerformance", APQP_ResourceActivityTracking" and "APQP_ResourceLoading"
6. Need to give proper spacing and removing _ in the names of "APQP_ApprovalChart", "APQP_OnTimePerformance", APQP_ResourceActivityTracking" and "APQP_ResourceLoading" (These changes needed in Menu also)
7. "Issues" have no usage in Team Member Activities section, so can remove this rights
| 8. Sugestion . Disable the checkbox selection for the default groups like PM and Resource |  | Raghu need to work on it
Emails
| Url's are not showing with hyperlink when getting in inbox | Link option given
1 | Pending task reminder mail content is not correct Project completed- Content need to modify with Regards and break line | Given
2 | Task Assigned ,Task Completion - Project Manager , New Program Created ,Task Revised - ,Space need after the link On baseling a project , without assigning new task the mail will be triggered with emplty datain tabular columns | url is given as Hyperlink - in new mail content | closed
3 | Task Escalation - Scheduled date spelling incorrect, Mail is addressing to PM twice(baseline also), Before escalation mail content need modification | Position wise user also showing
4 | Document Creation Notification - Header footer not avail(Task owner to project Owner) | Not needed now
5 | Project Created under Program,- Line break needed for the contents( applicable to almost all mails) and space needed after link | url is given as Hyperlink - in new mail content | closed
6 | Mentor mail content is duplicate | Given | closed
7 | Project Completed- Content modification, line brk needed | Given | closed
8 | Predecessor date shift shows run at date as one day after the submission | Need to check
9