## Medium&Low
S.No | Functionality Page | Issues | Priority | Reported By | Responsible | Dev Priority | Dev Status | QA Status
11 | competency evaluation | It should be select user/nonemail users | low | Manaswita | Manaswita | 0 | Not an issue | Fixed
17 | Job Requirements | there are no option to evaluate role ( Column pos -> role and role should be displayed at the top) | medium | Manaswita | Ramakrishnan | 0 | Fixed | Fixed
19 | Courses | List of trainings are not showing all the trainings | medium | Manaswita | Ramakrishnan | 0 | Fixed | Fixed
20 | Training Request | Training course field should be mandatory | low | Manaswita | Gurumurthy | 0 | Fixed | Fixed
25 | Records | Training Records -> Date scheduled sorting not working | Medium | Prasanna | Ramakrishnan | 0 | Fixed | Fixed
26 | Records | Maximize icon in training records popup(Max and min icons in all popups) | low | Prasanna | Monisha | 3 | Fixed | ?
30 | Job Requirement | On disabling a pillar in competency criteria, pillar are not removed on closing the popup(Only getting removed when refreshing the page) | medium | Belwinsha | Gurumurthy | 3 | Fixed | Fixed
31 | Job Requirement | Disable trained,awarded and experienced legends when process competency is disabled and no data found in pillar when enabled, Add legend for green and yellow(competent and required level) | medium | Belwinsha | Gurumurthy | 3 | Fixed | Fixed | Need to remove full stop after "No Data found"
32 | Job Requirement | Collapse is not working for the accordion view¦ keep add button and search box in change view | medium | Belwinsha | Ramakrishnan | 6 | Inprogress
33 | Job Requirement | Position and role dropdown change it to control dropdown( height should be static with scroll). Should be a searchable dropdown | medium | Belwinsha | Gurumurthy | 3 | Fixed | Fixed
34 | Job Requirement | Accordion view-> not expanding when data is not there, instead show no data found | medium | Belwinsha | Ramakrishnan | 0 | Fixed | Fixed
37 | Job Requirement | POsition documents icon should show, revision,document owner,document number details | low | Belwinsha | Gurumurthy | 4 | Fixed | Fixed
38 | Job Requirement | Auto close saved successfully alert, deleted successfullt alert and all alerts | low | Belwinsha | Monisha | 0 | Fixed | Fixed
42 | competency evaluation | It is taking more time to load the page after selecting the user | low | Manaswita | Gurumurthy | 4 | Working fine | Fixed
46 | competency evaluation | Once user remove the user, page is not refresing automatically | low | Manaswita | Gurumurthy | 4 | Not replicating | Fixed
47 | Job Requirement page and import popup | Role Position switch box is not working often | low | Belwinsha | Ramakrishnan | 0 | Fixed | Fixed
50 | Consolidation and Schedule | Preselect training request in consolidation and edit schedule | low | Belwinsha | Ramakrishnan | 4 | Not an issue | Fixed
57 | Import Job Req | Import Job requirement content is wrong.. It shows training information | medium | Belwinsha | Ramakrishnan | 0 | Fixed | Fixed
Instead of excel format -> Instructions
60 | competency evaluation | Auto close alerts | low | Belwinsha | Monisha | 0 | Fixed | Fixed
61 | Detailed competency evaluation | Maximize is not working | low | Manaswita | Monisha | 0 | Fixed | ? | Not working in my machine
62 | competency evaluation | Maximize not working when clicking training request from competency | low | Belwinsha | Monisha | 0 | Fixed | ? | When i expand the popup goes down the screen
64 | competency evaluation | Label Name changes: | low | Belwinsha | Monisha | 0 | Fixed | Fixed
Comp action popup:
status -> Status
Created Date -> Submitted Date
65 | competency evaluation | Comp action popup: Show Submitted date only when action is assigned | low | Belwinsha | Gurumurthy | 4 | Fixed | Fixed
66 | competency evaluation | Comp action popup: Buttons are not sticky | low | Belwinsha | Monisha | 0 | Fixed | Fixed
68 | competency evaluation | Uploaded By column is attachment listing | low | Belwinsha | Gurumurthy | 4 | Fixed | ?
70 | competency evaluation | Rename list of users to competent users(3 dots) | low | Belwinsha | Monisha | 4 | Fixed | ?
79 | My Competencies | Adding certificates- getting duplicated | medium | Belwinsha | Monisha | 1 | Fixed | Fixed
Close expiry date popup after attachment alert
Popup design not good
80 | Competency evaluation | Employee not getting selected automatically in training request from My competencies | low | Belwinsha | Gurumurthy | 4 | Fixed | Fixed
82 | My Certifications | Expiry date is not displayed | low | Belwinsha | Gurumurthy | 4 | Fixed | Fixed
84 | Training | Include completed training switch box, only when data has completed trainings | medium | Belwinsha | Gurumurthy | 1 | Fixed | Fixed | Not Fixed
(After enabling the option completed training is not listing)
91 | Training | Training status column border is missing | low | Belwinsha | Monisha | 4 | HOLD
93 | Training | Data mismatch in training tab | low | Belwinsha | Monisha | 4 | HOLD
94 | Training | Except Training Name and Trainer, other columns are not getting searched | low | Belwinsha | Monisha | 4 | Fixed | ?
95 | Training Request | Remove filter for view log in training request | low | Belwinsha | Monisha | 4 | Fixed | ?
96 | Training Records | Remove mandatory indication for Training name,Date in record edit | low | Belwinsha | Ramakrishnan | 4 | Fixed in local
97 | Training Records | Training record -> course description should be renamed to Training Name | low | Belwinsha | Gurumurthy | 1 | Fixed | Fixed
98 | Training Records | Keep Select Questionnaire beside the text box(inlined) | low | Belwinsha | Gurumurthy | 4 | Fixed | ?
99 | Training Records | Select Questionnaire popup -> table format with done | low | Belwinsha | Gurumurthy | 4 | Fixed | ?
remove outside space inside the iframe
101 | Training Records | Rename Date scheduled -> Training start date | medium | Belwinsha | Monisha | 1 | Fixed | Fixed
Training Start Date, Training End Date, Completion Date
106 | Evaluation | Department should be actual department | low | Belwinsha | Monisha | 5 | Fixed in local
112 | Annual Trg Plan | Annual Training Plan not opening | medium | Belwinsha | Monisha | 4 | Fixed | ?
113 | Training | Remove employee name in filter | medium | Belwinsha | Monisha | 4 | Fixed | Fixed
116 |  | In status dropdown it shows only one and not needed for dropdown on Competency action | low | Yamuna | Gurumurthy | 4 | Fixed | Fixed
120 | Training Request | Duplication in training documents in training request(only for few docs) | medium | Belwinsha | Gurumurthy | 2 | Fixed | Fixed
124 | Records | View log is not working, showing "Loading". Training name-CQI3 | Medium | Manaswita | Ramakrishnan | 2 | Unable to replicate | Unable to replicate
127 | Training tab | Created schedule is not reflecting in Training tab (Admin login) | Medium | Manaswita | Ramakrishnan | 1 | Fixed | Fixed
128 | Employee Management-->Additional Information | Competencies are not reflecting in competency dropdown | Medium | Manaswita | Ramakrishnan | 1 | Fixed | ?
132 | Records | Auto close is not working after selecting the survey or evaluation | Low | Manaswita | Monisha | 2 | Inprogress
134 | Systems-->Role-->Add | there should be 1space between RoleName | Low | Manaswita | Monisha | 1 | Fixed | Fixed
160 | Training | Training Calender: Filter name is hided behind the toggle button | Medium | Yamuna | Monisha | 2 | Fixed | Fixed
161 | Competency Evaluation | The competency action popup shows more white space at below & need to remove blue shadow behind | Low | Yamuna | Monisha | 2 | Fixed | Fixed
162 | Competency Evaluation | It shows new button option in Competency action | Medium | Yamuna | Gurumurthy | 2 | Fixed | Fixed
Sub date and status - display on inprogress and completed action(restrict for new)
Status dropdown should be similar to the status outside
status should hold inprogress and completed options for inprogress action
Restrict save button for completed action
164 | My Competencies | On Adding certificate->System opens the same attachment popup for both clicking on Submit & Cancel | Medium | Yamuna | Monisha | 2 | Fixed | ? | Unable to check due to add cerificate issue
165 | Competency Search | In Competency Search the Position/Role column is not changing by default once it is set with position/role(User has to refresh the page again) | Medium | Yamuna | Gurumurthy | 2 | Fixed | Fixed
167 | Competency Evaluation | Without selecting employee if we directly select Employee against position in Competency evaluation page shows server error | Medium | Ragavi | Gurumurthy | 3 | Fixed | ?
169 | Job requirement | Note for Comma seperation is not needed in the Edit in Job requirement page | Medium | Yamuna | Monisha | 3 | Fixed | ?
170 | Detailed competency evaluation | Expand is not working in Detailed competency page | Medium | Yamuna | Monisha | 3 | Fixed | ? | Not working in my machine
171 | Detailed competency evaluation | Required level & level of competency search is not working in Detailed competency | Medium | Yamuna | Monisha | 2 | Fixed | Fixed
173 | Job requirement | Tool tip in Job requirement page is not showing Edit/delete | Medium | Yamuna | Gurumurthy | 1 | Fixed | Fixed
174 | Competency evaluation | In Role selection when selecting multiple users the update competency button is not showing | Medium | Yamuna | Gurumurthy | 3 | Fixed | ? | Update button is not working & when one employee is selected the data is not loading
175 | Training Records | Source of Training is showing as PDP by default in adding new Training Records | Medium | Yamuna | Monisha | 5 | Fixed | ?
187 | Training Request | The plus icon (to add more course) near the training course field is not working | Medium | Yamuna | Ramakrishnan | 3 | InProgress
188 | Course | In master course adding popup the Training name column is blank | Low | Yamuna | Gurumurthy | 4 | Not an Issue | Fixed
189 | Job requirement | Only In SKILL pillar after editing the plus icon is not working | Medium | Yamuna | Gurumurthy |  | Fixed | Fixed
190 | Detailed competency evaluation | When required level search is done->it shows including the N/A value when user selects for both Level 1 & Level 6 | Low | Yamuna | Gurumurthy | 4 | Fixed | Fixed
192 | Competency Action | In competency action user is not able to do attachment(after uploading the document gets invsible) | Medium | Yamuna | Monisha | 3 | Fixed | Fixed
196 | Training Schedule | Facing duplication in Training schedule page after adding 5 participants | Medium | Yamuna | Ramakrishnan | 3 | Fixed | ?
200 | Training Schedule | Participants duplicating in participants grid | Medium | Yamuna | Ramakrishnan | 3 | Fixed | ?
204 | Courses | End date automatic fetching is also not working in creating Training schedule from Courses page | Medium | Yamuna | Monisha | 4 | Fixed | ? | For exisiting couses it works but for new courses its not working
205 | Courses | From course series page not able to schedule training | Medium | Yamuna | Gurumurthy | 4 | Working fine | Fixed
206 | Trainign Record | Training Records -> status, completion date and Survey initiated filter not working | Medium | Belwinsha | Ramakrishnan | 3 | Fixed | ?
| Job requirement page | Import is not working for Position based | Medium | Yamuna | Ramakrishnan | 5 | ?
| Email | Email->Need to add the Start Date (including time) and End Date (including time) to the Training Consolidated-Faculty Emails is not hitting to Batch | Medium | Yamuna | Gurumurthy | 5

## Suggestions
S.No | Functionality Page | Issues | Priority | Reported By | Responsible | Dev Priority | Dev Status | QA Status
27 | Training Records | Format popup design should be changed | Suggestion | Prasanna | Gurumurthy | 5 | Fixed | ?
63 | competency evaluation | By default, view documents in a table below in Competency action popup | Suggestion | Belwinsha | Gurumurthy | 6 | InProgress
69 | competency evaluation | Status Log for Actions | Suggestion | Belwinsha | Monisha | 6 | InProgress
78 | Competency Search | Change eye icon under Proof column in comp search (We can keep document icon) | Suggestion | Belwinsha | Monisha | 1 | Fixed | Fixed
81 | My Certifications | Checkbox is not needed beside employee | Suggestion | Manaswita | Gurumurthy | 5 | Fixed | ?
89 | Training | Training Log | Suggestion | Belwinsha | Monisha | 6 | InProgress
92 | Training | Surver Initiated column in training page | Suggestion | Belwinsha | Monisha | 4 | Fixed | ?
100 | Training Records | Differentiate new training record which is created directly in records page | Suggestion | Belwinsha | Ramakrishnan | 6 | InProgress
103 | Evaluation | Remove Submission type column-> instead add Action Status(Survey Assigned/Survey Completed/Survey Not Initiated) | Suggestion | Belwinsha | Monisha | 6 | InProgress
(Evaluation Assigned/Evaluation Completed/Evaluation Not Initiated)
104 | Evaluation | Rename Course Description -> Training name(Grid and inside evaluation) | Suggestion | Belwinsha | Gurumurthy | 1 | Fixed | Fixed
105 | Evaluation | Evaluation design change | Suggestion | Belwinsha | Monisha | 6 | InProgress
107 | Evaluation | View icon -> is participant attended -> show the document which is submitted by Employee | Suggestion | Belwinsha | Monisha | 6 | InProgress
108 | Course | Headers are not bold -all pages (Course details etc) | Suggestion | Belwinsha | Monisha | 4 | Fixed | ?
109 | Business rule | Ample - business rule in Business rule | Suggestion | Belwinsha | Gurumurthy | 6 | Fixed in Local
110 | Competency Evaluation | Categorize competency trainings | Suggestion | Belwinsha | Monisha | 4 | InProgress
111 | Schedule | Differentiate new doc training or Change request doc training | Suggestion | Belwinsha | Monisha | 6 | InProgress
114 | Competency | Can replace the funnel icon with search icon in the job requirement page in Competency mngt | Suggestion | Yamuna | Monisha | 4 | Fixed | ?
115 |  | Can make expand option for all pillars in Change view option | Suggestion | Yamuna | Monisha | 4 | InProgress
139 | Training Record History | Reset option is needed | Suggestion | Belwinsha | Ramakrishnan | 6 | InProgress
151 |  | By mistake i attached the document, how can i remove the attachment | Suggestion | Prasanna | Gurumurthy | 6 | InProgress
179 | Job Requirement | Required level should hold instruction for uploading competency | Suggestion | Belwinsha | Monisha | 5 | Fixed in local
195 |  | Dropdown in request(Position based training, position document based training, role based training) | Suggestion | Belwinsha | Ramakrishnan | 5 | HOLD