## 11322 HF
S.No | Page | 11.3.2.2 Release Items | Category | Responsible | Status | Patch Moved (Yes/No) | Unit Testing Results | QA status | Comments
1 | Mate Risk form | add risk action - after selecting 3 to 4 times records in add risk action popup ,again unable to add records on selecting records there is no response | low | surya | Fixed | yes | working | Fixed
2 | MATE - Change request status page | status page Part name shows mate form internal part number data | low | Surya | hold | Hold | Hold | Hold
3 | CR form termination & Rejection with adhoc route | Step1:CR IS Published with adhoc approval, |  | Monisha | Fixed in 1132 | Yes | Working | Fixed | Rejection and termination is now taking category approval on revising the CR
Step 2:The requestor terminated the action,
Step 3: Resubmit the CR form
Step 4: Check for the approval section(it wont show the category approver if set)
Step 5: Publish the CR again
Step 6: Publish is not working, status still showing as open and form shows all buttons
4 | non mandatory approver - Business rule | non mandatory approver business rule enabled in business rule setup but published form in doc pro ,not showing non mandatory approvers | low | Monisha | Fixed | Yes | Working | Fixed
5 | customer waiver approval setup | Designation get saved without selecting Approver. (scenario for existing record : without selecting approver we can save different designation for the particular record ) | low | Surya | Fixed in local | ?
6 | view log | when main form get terminated- view log approver section shows wrong user ( instead of approver name , now showing initiater name ) | low | Surya | Fixed | yes | working | Fixed
7 | streling form | 1.document to change section - document name section is editable , need to lock document name section | low | surya | Fixed | yes | working | Fixed
2.action item section is editable, need to lock
3.Target date not getting saved for cft - added by right click add functionality
4.include other document action completion not validating during CN publish
8 | APQP | source ref. not generating , if we initiate change request from APQP | low | Monisha | Fixed | Yes | Working | Fixed
9 | Mail | change request rework - while opening hyperlink, whether need to show buttons ? | low | Monisha | Fixed | Yes | Working | Fixed
10 | widgets - Terminated status | Terminated status - while opening terminated status change request from widgets, instead of CR form its shows CN form | low | Monisha | Fixed | Yes | Working | Fixed
11 | ECR - CFT Section | 1.initiate ECR change request form | low | Surya | Fixed | yes | working | Fixed
2.navigate to cft section
3.delete cft user populated from setup
4.add new cft by right click add
5.click on submit to team button
6.navigate to cft section ,try to complete sign off
ISSUE: after clicking submit to team button initiater can able to approve the form
Note : Applicable for all ECR duplicate forms
12 | Status page - Multi search | 1.change request number - equals, Not equals,contains, start with, ends with, Not contains | Issue | Surya | Fixed | Yes | working | Fixed | 1.not equals , not contains -- FIXED
|  | 2.change subject - equals , start with | [6 empty] | 3.not equals , not contains -- FIXED
|  | 3.Change category - equals , not equals, start with , ends with, not contains | [6 empty] | 4.not equals , not contains -- FIXED
|  | 4.Requested by - equals, not equals, start with, contains,ends with | [6 empty] | 5.not equals , not contains -- FIXED
5.project - equals , Not equals
13 | CR Form setup | 1.Click on subform map template | low | surya | Fixed | yes | working | Fixed
2.navigate to additional settings
3.select folder for documents and click on save button
4.navigate to template settings map form and save it
5.navigate to additional settings , map folder, route, reviewers and save it
6.navigate to template settings & again navigate to additional settings
ISSUE: on second time navigation mapped data's not showing but after refresh data's listing
14 | Engineering change request | 1.action item section auto populated data need to lock | low | Surya | Fixed | yes | working | Fixed
15 | Copy functionality & Mandatory change title | 1.Mandatory change title business rule enable | low | Surya | Fixed | yes | working | clarity | 1.Business rule enable - while copying from status page, CR number not generated -- FIXED
|  | 2.initiate change request | [6 empty] | 2.Copy form functionality not working for common functionality --- FIXED
|  | 3.observe numbering format | [6 empty] | 3.Approved status CR Form also Top Right corner numbering showing
|  | 4.enter change title and observe top right corner of form | [6 empty] | 4.CN Form also Top Right corner numbering showing,,, is that ok ?
5.click on copy form button
6.observe numbering format
7.enter change title and observe top right corner of form
ISSUE: when mandatory change title business rule enabled, while performing copy functionality, that copied form numbering format section in top right corner of form is not showing
16 | Additional approver functionality | 1.Initiate PCR form | low | Surya | HOLD | HOLD | HOLD | HOLD | 1.While publishing CN form action item getting for both category & maura approver ( round of approver functionality not working )
2.select additional approver check box
3.enter mandatory fields
4.observe CR approver section and publish it
5.under - underview status observe CR approver section
6.approve the form and open CN from status page
7.observe CN approver section
ISSUE: By default additional approver and category approver not showing in CN approver section ( now category approver only showing by default )
17 | Mandatory change title business rule enable | 1.Enable mandatory change title business rule | low | Surya | Fixed | yes | working | Fixed
2.navigate to numbering format setup
3.select numbering format in set default numbering format setup
4.Remove numbering format against mapped category
5.initiate change request
6.observe top right corner numbering format section
7.enter change title and observe top right corner numbering format section
ISSUE: even after entering change title ,Numbering format not generating in top right corner numbering format section
18 | Attachment | 1.initiate change request | low | Monisha | Fixed | Yes | Working | Fixed
2.add attachment in attachment section (present , proposed )
3.publish the form and approve it
4.open CN from status page
5.navigate to attachment section and right click on it
Issue :Need to restrict right click add/delete option in CN - for proposed , present attachment section
19 | ECR - Team sign off - Target date section | 1.Remove all cft user in cross functional team setup | low | Surya | Fixed | yes | working | Fixed | 1.Try with added row delete and remap cft with target date -- Fixed
2.initiate change request
3.navigate to CFT section
4.By using right click add , add new row and cft user
5.Select Target date
ISSUE : Target date not getting saved
Scenario : without any cft user from cross functional team setup, when we initiate CR , newly added row target date not getting saved
20 |  | 1.initiate ECR Form |  | surya | Fixed | yes | working | Fixed
2.naviagte to include other document section
3.Map document from doc pro
4.Fill data's in action item section
5.Publish the form and approve it
6.Login as responsible person
7.open include other document action item
8.attach attachment
9.try to open attached attachment
ISSUE: on opening action items action , include other document section attachment row getting duplicated ( scenario : initiater , include other document , action item user are same )
21 | change setup - actions | Change category popup search not working |  | surya | Fixed | yes | working | Fixed
22 | MG Form | 1.Include other document section attachment getting duplicated |  | surya | Fixed in local | yes | working | Fixed
2.sub supplier form - confirmation section - attachment not getting saved
23 | Auto approval | 1.set auto approval . | High | monisha | Fixed | Yes | Working | NOT FIXED | 1. CN form approver section shows worng user by default listing but after publish its shows correct - Not an issue
|  | 2.initiate change request by aero | [6 empty] | 2.NOT FIXED
3.observe approval section
4.publish the change request by jayasurya
5.observe approval section
6.observe log details for approval
ISSUE: 1.CR published by jayasurya but approver section showing as aero
2.For CN Case - Not able to approve the request , on clicking approved check box form keeps on loading
24 | Log | 1.open CN form | Medium | Surya | Fixed | yes | working | Fixed
2.publish it
3.Reject CN form & observe log
4.republish CN form
5.Terminate cn form & observe log
6.republish cn form
7.Reject CN form & observe log
8.republish CN form
ISSUE : on multiple times reject / terminate - log not shows content
25 | risk setup | 1.once same data entered for two different category, if we make any edit it shows "already exists " alert |  | Surya | fixed | yes | working | Fixed
2.not able to make edit in low, medium, high risk section . it shows "parameter already exists" alert
26 | doc pro - documents to change sub form | 1.publshed subform in doc pro - while opening attachments, its says "revision number linked with the document is not available" |  | Surya | Fixed in local | Yes | working | NOT FIXED | 1.FIXED
|  | 2.revision number link is not clickable | [6 empty] | 2.NOT FIXED
27 | ECR form - include other document section | include other document section -- Revised document name section showing default document after publishing CR form | Fixed in local | Monisha | Fixed | Yes | Working | Fixed
step 1: initiate engineering change request form
step 2: navigate to include other document section
step 3: add document from doc pro
step 4: publish the form and approve it
step 5:open CN from status page
step 6:navigate to include other document section & observe revised document name section
issue : 1.revision number need to given as center aligned
2.is there any possibility to give document number & document name section as non editable
28 | MG Vave | MG Vave idea form name editable- need to lock ( top lable ) | Fixed | Surya | Fixed | yes | working | Fixed
29 | customer waiver approval | while searching - designation , approver fields , search not working | Fixed | Surya | Fixed | yes | working | Fixed
issue : 112016 Hf
30 | Group Rights page | view change requests menu need to give as seperate label | suggestion | Surya | Fixed | yes | working | Fixed
31 | view status icon - Mouse hover | view status icon mouse hover ( Tool Tip ) , Tool Tip need to rename based on view status icons listing / Hiding | suggestion | Surya | Fixed in 11.3.2 | yes | working | Fixed
32 | rework - mail | from hyperlink not able to open form , showing " Data cannot be found issue " | Medium | Monisha | Fixed | Yes | Need to check in cloud | Fixed
33 | finance & document & breakpoint subforms | finance & document & breakpoint subforms - if cft user reject the subforms, in view log status section shows signed off , instead of signed off ,need to give status as "Rejected " | Suggestions | Monisha | Fixed | Yes | Working | Fixed
34 | business rule- reject CR on team sign off - enable | let us assume 3 cft user in change request- if 1 st cft user reject the form , status changed to rejected. | High | Surya | Fixed | Yes | Working | Fixed | 1.rejected status - view status & Change Request Form is waiting for team sign off alert not getting changed - Fixed
|  | Issue : 1.view log - shows waiting for approval " for 2 nd, 3rd cft user with modify approver, terminate icon | [6 empty] | 2.on clicking revise document button , log shows partial data-- Fixed
|  | 2.action item not removed for 2 nd, 3 rd cft user | [6 empty] | 3.cft rejection log content missing -Not an issue
|  | 3.Disable reject CR on team sign off ( ECR form)- if cft user click on no check box , then in view log status showing as rejected ,, is that ok? | [6 empty] | 4.on clicking revise document button , form getting reload but view status & validation alert not getting reverted- Fixed
35 | document subform | pdf file format not opening from revision number link | low | DocPro | Inprogress | Docpro | Docpro | Doc pro
36 | subforms - responsible person action item | 1.open responsible person action item | low | Monisha | Fixed | Yes | Working | Fixed | 1.Page close automatically after clicking close icon in saved successfully alert , ,, is that ok ?
|  | 2.select target date / output attachment / completion date | [6 empty] | 2.FS Team patch missed -- FIXED
3.click on submit button
ISSUE : after clicking submit button, we can able to edit data's in subform ( note : after clicking submit button, need to close that page automatically )
Team Sign off Action - On clicking Approve/Reject checkbox need to close the window
37 | Subform resp person action submission | After submitting to team the submit button is removing from subform only after url refresh | suggestion | Surya | Fixed | yes | working | Fixed
38 | Reassign requester | 1.initiate change request ( user 1) | suggestion | Surya | Fixed | yes | working | Fixed | 1.user selection popup UI need to change-- Fixed
|  | 2. publish the form | [6 empty] | 2.content name need to rearrange " To " & " by" -- Fixed
|  | 3. By reassign requester functionality change requester as ( user 2) | [6 empty] | 3.if we change reassign requester by other module admin user its showing as requester only not as changed user--Fixed
issue: in underview status able to change requester is that ok ?
--- Add reassigned requester in log-----
39 | reassign requester - closed status | reassign requester functionality need to restrict for closed status | suggestion | Surya | Fixed | yes | working | Fixed
40 | Termination & Rejection with adhoc approver | Termination & Rejection with adhoc approver - initiate change request with auto approval - change approver by using assign approver button - publish it - terminate it - click on revise document button - publish it - observe CN approver section ( Issue : CR form get auto approved but CN form showing adhoc approver by default listing but on publishing CN get auto approved ) | medium | Monisha | Fixed | Yes | Working | Fixed
41 | Termination & Rejection with adhoc approver | Rejection with adhoc approver - CN rejection case - Rejected check box not getting updated ( Issue: CN rejection check box not geting updated) | low | Monisha | Fixed | Yes | Working | Fixed
42 | subform - maximize, minimize icon | need to remove blank white space in bottom of the subform | suggestion | Surya | Fixed | yes | working | Fixed
43 | status page - search | search not working ,if we do multiple times search in status page | medium | Surya | Fixed | yes | working | Fixed
44 | OS Site Changes | Include Customer & Module columns in alll CR listing page. | CR | Surya | Fixed | yes | working | Fixed
45 | OS Site Changes | Include Customer, Module, and JIRA Ticket for Problem fields in the Change Request Report. | CR | Monisha | Fixed | Yes | working | Fixed
46 | RSB | Risk Rating issue |  | Monisha | Fixed | Yes | working | Fixed
47 |  | 1.create new vave idea category |  | Monisha | Fixed | Yes | working | Fixed
2.initiate vave idea request ( newly created category )
3.navigate to status page
4.observe newly initiated vave request
ISSUE : vave idea request getting duplicated in status page , if we initiate vave
48 | change coordinater - duplicate user | 1.map change co ordinater user in additional settings |  | Monisha | Fixed | Yes | working | Fixed
2.map same change co ordinater user for subform cft reviewer
3.initiate change request
4.navigate to subform
5.observe cft section
ISSUE : cft user got duplicated if we map same user for change coordinater & subform cft review user
NOTE : Applicable for main form also
49 | risk form - rating values | Risk form - on unchecking the check box , rating value need to give as " 0 " value |  | Monisha | Fixed | Yes | working | Fixed
50 | purpose of change , consideration setup | purpose of change setup - PQCDSM Popup - search functionality not working |  | Monisha | Fixed | Yes | working | Fixed
51 | Internal | Exception log in new page, Formrequest and get approved project details |  | surya | Fixed in local | Yes | working | Fixed
| Doc pro | Documents left menu --> Documents --> CM main form folder publish -->Select form --> Navigate to Reference Attachments section --> Click on view --> Try to open PDF, TXT, HTML Format |  | Monisha | Not Replicating | Not Replicating | Not Replicating | NOT FIXED
Issue : pdf, html, txt format file not opening through reference attachment section
53 | log - subform | 1.set auto approval for subform | High | Monisha | Fixed | Yes | working | Fixed | Log content missing -- Fixed
2.initiate change request with user 1
3.publish the subform with user 2
4.observe subform approver section & log details
ISSUE : Subform showing user 1 as approver in form but in Log its shows user 2 as approver
54 | log | 1.subform - once subform get rejected & after republish , Republished log content missing ( submitted & completion log ) |  | Surya | fixed | yes | working | Fixed
2.subform - Termination log & after republish , Republished log content missing ( submitted & completion log )
55 | Action management - change request action - Dept action - submit button | 1.initiate change request ( user 1) | High | Surya | Not Replicating | Not Replicating | Not Replicating | Not Replicating | 1.For Dept review we need to complete action from action management only ( not from status page )
2.navigate to subform
3.select responsible person ( user 2), target date - submit action item
4.click on submit to team button
5.login as user 2
6.navigate to status page , open change request
7.From status page complete dept review & change request actions
8.login as user 1
9.navigate to status page, open change request
10.observe view status icon colour & action waiting alert
ISSUE: if we perform action completion in status page , that status not get updated in view status
56 | log | 1.subform - Need to include Termination status in log , now termination log missing | High | Surya | fixed | yes | working | Fixed | 1.Fixed
|  | 2.main form - CR is rejected by aero content showing after clicking publish button , need to give that content before clicking publish button | [6 empty] | 2.need to show rejected status log content before revised document log content - After clicking revise document button -- Fixed
57 | Action management - Site column | 1.create user in corporate site |  | Surya | Fixed | yes | working | Fixed
2.navigate to multi site
3.map created user (corporate) in responsible person action and submit it
4.login as responsible user
5.navigate to action management
6.observe site column
ISSUE: site column shows corporate instead of multi site
58 | view status icon | 1.set auto approval | High | Surya | Fixed | yes | working | Fixed
2.initiate change request
3.publish it
4.open CN form publish it
ISSUE: need to remove implemented icon in view status ( implemented status not applicable for auto approval )
59 | Michelin - PIPO | After entering data , Graph not showing in PIPO chart |  | Surya | Report Team
60 | supavut | VR Report -As multi site is included required a site filter in the report | low | Reports Team,Surya | Inprogress
61 | Default Folder | When default folder is enabled for the first time without subfolders then the CR getting published against the level set in BR. Once the Change management folder is created then it is working properly | low | Monisha | Not Replicating | Not Replicating | Not Replicating | Fixed | Will confirm after getting a blank DB( Working in customer training)
62 | ECR FG form APQP Integration | Schedule finish date showing one day less than the date given in the form |  | Monisha | Not Replicating | Not Replicating | Not Replicating | Not replicating
63 | Suggession | Suggesting to change Business rule name as Change management configuration |  | Surya | Fixed In local | yes | working | Fixed
64 | Suggession | Suggesting to include initiate cn button inside the published form |  | Monisha | Fixed | Yes | working | Fixed
65 | subform - maximize, minimize icon | subform - maximize, minimize icon not working properly, if we open multiple subforms one by one | High | Surya | Fixed in local |  |  | Fixed
66 | Vistor form | pdf view restriction for vistor form add in business rule | High | Monisha | Fixed | Yes | working | Fixed
67 | Popup height issues | 1.while initiating change request - main form popup need to give as fit to screen | suggestion | Surya | Fixed | yes | working | Fixed | 1.blank white space showing at bottom of the form while initiating -- Fixed
|  | 2.need to remove blank white space in all subforms | [6 empty] | 2.small white space showing at bottom -- Fixed
|  | 3.while reducing main form zoom size , that time while opening subform, subform view need to adjust based on the main form view | [6 empty] | 3.not fixed
|  | 4.while clicking maximize / minimize icon in subform, blank white space appearing in bottom of the subform | [6 empty] | 4.not fixed
68 | customer waiver approval | let us assume 4 users ( user1,user2,user3,user4)in customer waiver approval section, and the action item is submitted for approval, then login with user4 and open change request from status page , now for the user 4 checkbox are enabled in customer waiver approval section but there is no action item submitted for that user |  | Surya | Fixed | yes | working | NOT FIXED | 1.Not able to add new data -- Fixed
69 | doc pro - documents | if we set initiator as approver for subforms, then published form in doc pro shows , approver check box as unchecked |  | Surya | Fixed | Yes | Working | Fixed
NOTE : fix already given in 11204 hf
70 | document subform | right click add functionality - actual date is editable for Requester ,need to lock actual date section | Fixed in local | Monisha | Fixed | Yes | working | Fixed
71 |  | 1.remove additional settings for subform | fixed | Surya | fixed | yes | working | Fixed
2.initiate change request
3.observe route for main and subform
4.by using assign approver button change approval route
5.observe main and subform route
6.publish the subform
7.observe viewlog
ISSUE: We changed approver by using assign approver button but in viewlog listing & approval its going for old approver
72 | multi disciplinary approach | if we remove all the cft user in multisisciplinary approach section | Fixed | Monisha | Fixed | Yes | working | clarity | 1.NOT FIXED
1.reviewers not mapped subform - while try to add row by right click, rows getting duplicated in top of the form
2.while clicking submit to team button, it shows alert but notify team check box got checked
73 | view status icon | view status icon - icon colour need to change after the dept / team sign off functionality done ( now colour changing after refresh only ) | suggestion | Surya | Fixed | Yes | working | NOT FIXED | 1.Dept review,approval , CN actions not handled-- Not Fixed
|  | ISSUE : if we submit dept review after the refresh only dept review view status icon clour getting changed to orange | [6 empty] | 2.subform - action, dept review, team sign off, approval not handled
3.Dept review - After action submit form not get reloading-- Fixed
4.Notify not handled--- ?
5.while clicking CN Dept review ,its shows CR form-- ?
6.while clicking CN Team sign off , its shows CR form-- ?
7.subform - on reloading ,by default view status Timeline is Hiding
8.Dept review - After action submit form not get reloading-
9.team sign off ,approval
10.while clicking CR notify , it redirects to CN
74 | Termination Rejection Scenario for Gabriel | 1. When Category Approver + Marua is set up then On terminating the request and resubmitting the approval section shows blank and not allowing to publish( Showing open status after Publish) | High | Monisha | 1.Fixed | Yes |  | FIXED
2. When multiple approvers are there then on teminating the log showing the record multiple times(This may be addressed with new change in termination log)
75 | RSB | Swap the rows i.e. "Stock available" and "Horizontal Deployment" in CN form | Change Request | Monisha | Fixed | Yes | working | Fixed
76 | RSB | Swap the rows i.e. "Feasibility study" and "Risk analysis" in CR form. | Change Request | Monisha | Fixed | Yes | working | Fixed
77 | RSB | Need to include " Risk Description" in Risk Analysis sheet | Change Request | Monisha | Fixed | Yes | working | Fixed
78 | close icon | The close icon in the change request form looks small; it needs to be slightly bigger | suggestion | Surya | Not an issue | Not an issue | Not an issue | Not an issue
79 | configure column | configure column - while clicking maximize & minimize icon , page not restoring properly |  | Surya | Fixed in local | yes | working | Fixed
80 | Requested by name in status page | 1.initiate change request | low | Monisha | Fixed | Yes |  | Fixed
2.observe requested by name section
3.edit user name in suite
4.navigate to status page
5.observe requested by name in form
6.observe requested by name in status page
ISSUE: once we edit user name in suite , edited user not get updated in status page requested by section but inside the form requested by name getting changed
81 | CM Setup | change management setup menus not allowing to enter special character ( !@#$%^&*()_+) | low | Surya | Fixed in local | yes | working | Fixed
82 | log | CFT - termination status log content need to include in Log functionality | suggestion | Surya | Not an issue | Not an issue | Not an issue | Not an issue
83 | CFT Termination | Comments - Terminated need to give centre aligned for main & subform | suggestion | Surya | Not an issue | Not an issue | Not an issue | Not an issue
84 | Existing DB - CM Setups - Page navigation issue | 1.open purpose of change setup | low | Surya | Fixed | Yes | working | NOT FIXED
2.add new data
3.make newly created data as inactive status & all other existing data as active status
4.by search filter , search active status
5.check for page navigation
ISSUE: showing 1 record extra in active status ( for example : in active status we have 31 records means its 32 records -- last page showing 2 record instead of 1 record)
85 | TDR | 1.Approved status - while opening view form link in associated TDRs section , there is no response | low | Monisha | 1.Not an issue 2.Fixed | Yes | working | Fixed
2.doc pro - not able to open attachment link, view form link in published form
86 | Action | Remove Submit button on team sign off action | low | Surya | Fixed | yes | working | Fixed | 1.from team sign off action item ,not able to edit responsible person action items row ( responsible person column is non editable ) -- Fixed
2.if team sign off & responsible person action assigned for same user , then top note alert is missing- Fixed
3.for responsible person action item also , top note alert is missing- Fixed
4.Responsible person section is non editable for requester- Fixed
5.if dept review & team sign off assigned for same user , then while opening dept review action item responsible person section is non editable,,,, is that ok ? --- Not an issue